## Learning Log
Date | Story | Old Points | New Points | Details | Who
2008-01-18 | 287 | 1 | 2 | in planning, javascript looked more complex than was estimated | Matt / SK
2008-01-18 | 391.2 | 2 | 1 | deploying is not that hard! | Matt / Ian
2008-01-18 | 239 | 2 | 0 | it's just a task, part of story 290 | Matt / Brett
2008-01-18 | 391.1 | 3 | 0 | done! (we only get one broker in the DMZ) | Matt
2008-01-18 | 282 | 1 | 3 | ideally we need to do the upload thru WAM so that the AAS doesn't get full of rubbish. We may also need to build a rough screen for managing the news data | Matt / Brett
2008-01-22 | 290 | 3 | 5 | added in points from 239 | Matt
2008-01-22 | 283 | 4 | 3 | not that hard, done as part of 290 | Matt
2008-01-23 | 296 | 1 | 2 | Covering all work Kellie and Johan will do to polish the OLC UI | Matt
2008-01-23 | 295 | 1 | 2 | I suspect this will turn out to be more complicated that one-pointer | Matt
2008-01-23 | 245 | 2 | 1 | this is ridiculously easy! | Matt
2008-01-23 | 416.1 | 5 | 0 | covered by 432 | Matt
2008-01-23 | 416.2 | 5 | 2 | a lot easier now that 432 is done | Matt
2008-01-23 | 297 | 0 | 2 | Story missed from list | Ian/Matt
2008-01-23 | 298 | 0 | 1 | Minor change request for new email boxes | Ian/Matt
2008-01-23 | 292 | 1 | 0 | this should never have been a story | Matt
2008-01-24 | 216.2.5 | 1 | 0 | deleted
| 415 | 13 | 5 | now much easier following other similar work on preview service etc
| 240 | 2 | 0 | should be done as part of 391.6
|  | 47 | 29

## Features (OLC)
ID | Target Release | Surface Point | Theme | Pts | Satisfaction Criteria | Feature | Status | Analysis required | Business Risk | Tech Risk | Last Reviewed | Plumbing Involved? & FP | Plumbing FP | CAPEX
124 | 1 | OLC UI | Welcome Page | 3 | 2.3 | As a non-authenticated user arriving at the OLC, I want to see a styled welcome page
127 | 1 | OLC UI | Security | 3 |  | Implement SSO Service and Client | [7 empty] | 3
131 | 1 | Team | Technical Design | 7 |  | Capture and communicate technical design elements of the project
26 | 1 | OLC UI | Welcome Page / Security | 6 | 2.1 | As a BBC staff member arriving at the landing page, I want to be able to register with the OLC site so that I can immediately start using the site
31 | 1 | OLC UI | Welcome Page / Security | 2 | 2.4 | As a registered user of the OLC who has forgotten their password, I want to be able to retrieve my password via email by entering my username
29 | 1 | OLC UI | Welcome Page / Security | 5 | 2.3 | As a registered user of the OLC, I want to be able to log in to the site from the welcome page and be taken to the homepage
59 | 1 | OLC UI | Global Navigation | 1 | 18.4 | As a logged in user viewing any page on the site, I want to see hyperlinks that take me to external websites like Motion Gallery, BBC Worldwide.
125 | 1 | OLC UI | Home Page / Layout | 3 | 10.x | After logging in, I want to see a styled homepage built from a standard template, with placeholders for the planned future content
28 | 1 | OLC UI | Update Profile | 2 | 2.2 | As a registered user of the OLC, I want to be able to view and amend my account details (email address, password, etc)
61 | 1 | OLC UI | Global Navigation | 2 | 18.6 | As a logged in user viewing any page on the site, I want a link that allows me to log out of the site
69 | 1 | OLC UI | Home Page | 4 | 10.7 | As a logged in user viewing the homepage, I want to see world news headlines from the BBC news website displayed as hyperlinks to those articles
60 | 1 | OLC UI | Global Navigation / Update Profile | 5 | 18.5 | As a logged in user viewing any page on the site, I want a link that takes me to a placeholder page where I will be able to view / edit my profile
81 | 1 | OLC UI | Global Navigation / Genre Homepage | 3 | 18.2 | From any page, I want to be able to navigate to a (blank) Genre Homepage by clicking on a Marketing Genre link in a left-hand-side menu
65 | 1 | OLC UI | Global Navigation / Search | 2 | 17.1 | As a logged in user viewing any page on the site, I want the standard page header to contain a quick search box
9 | 1 | OLC UI | Quick Search | 6 | 1.5 | User quick-searches for MarketingCatalogueItem(s) using a free-text search against Title, Working Title, Alternative Title, and Strand fields
10 | 1 | OLC UI | Search Results | 2 | 1.6 | Display a list of MarketingCatalogueItem titles as a result of a search (quick or advanced)
11 | 1 | OLC UI | Search Results | 2 | 1.6 | MarketingCatalogueItems that are inactive (see business rule #1) will never, ever be included in the search results
13 | 1 | OLC UI | Search Results | 2 | 1.6 | Show search results in pages
12 | 1 | OLC UI | Search Results | 6 | 1.6 | User gets a 'did you mean…' prompt from the search results if the free-text search was not an exact match but close to a real programme title (or other searchable field)
126 | 1 | OLC UI | Search Results / Programme Page | 2 | 1.6 | Clicking a search result item will take me to a (blank for now) Programme Page
32 | 1 | OLC UI | Programme Page / Header | 2 | 11.2 | Programme Page will display metadata about the MarketingCatalogueItem - Catalogue Item Title, Duration, TX Date, Available / Coming Soon, Is HD
36 | 1 | OLC UI | Programme Page - Programme Info | 6 | 11.4 | Tagline, Synopsis, Press Quotes, Awards, Contributors will be displayed on the programme info section
34 | 1 | OLC UI | Programme Page / Header / Favourites | 3 | 10.3 | It will be possible to add / remove a programme from my favourites from the programme page
58 | 1 | OLC UI | Global Navigation / Favourites | 6 | 17.2 | As a logged in user viewing any page on the site, I want to be able to access a list of my favourite programmes and navigate to that programme
23 | 1 | OLC UI | Favourites | 1 | 1.6 | User can see whether a MarketingCatalogueItem is in their favourites from the search results
33 | 1 | OLC UI | Favourites | 1 | 2.8 | Programme Page will display whether a MarketingCatalogueItem is in my favourites
1 | 1 | OLC UI | Advanced Search | 2 | 1.4 | Raw unstyled Advanced Search Screen, where user searches for MarketingCatalogueItem(s) using a free-text search against Title, Strand, Alt Title, Working Title
4 | 1 | OLC UI | Advanced Search | 0 | 1.4 | User refines the free-text search by specifying Duration
2 | 1 | OLC UI | Advanced Search | 0 | 1.4 | User refines the free-text search by specifying Marketing Genre
5 | 1 | OLC UI | Advanced Search | 0 | 1.4 | User refines the free-text search by specifying Available on HD
6 | 1 | OLC UI | Advanced Search | 0 | 1.4 | User refines the free-text search by specifying tv programmes / format only / both
123 | 1 | OLC UI | Genre Homepage | 2 | 12.1 | Basic Dummy Genre Homepage populated using search results for the given Marketing Genre
14 | 1 | OLC UI | Search | 2 | 1.6 | User can sort search results by title
74 | 1 | OLC UI | Home Page Links to Pages | 1 | 10.1 | As a logged in user viewing the homepage, I want a link to a page which lists programmes that support HD
| 1 |  |  | 94
204 | 2 | AssetArchive API | HasPreview Flag | 12 |  | AssetArchive offers web service call to insert an asset so that the ArchivePreviewService can update the archive when new assets become available | [7 empty] | 12
202 | 2 | AssetArchive API | HasPreview Flag | 6 |  | AssetArchive offers web service call to return the count of all preview assets for an ORAC episode so that OLC can display the HasPreview flag | [7 empty] | 6
18 | 2 | OLC UI | HasPreview Flag | 6 | 1.6 | user can see an indicator on the programme page which shows whether the AssetArchive Service is aware of any preview clips for each MarketingCatalogueItem
47 | 2 | OLC UI | HasPreview Flag | 1 | 2.7 | Marketing Materials section will indicate whether or not preview materials exist for this CatalogueItem
201 | 2 | AssetArchive API | HasPreview Flag | 4 |  | AssetArchive offers web service call to query all assets so that the OLC admin can display them | [7 empty] | 4
301 | 2 | OLC Admin | AssetArchive | 8 |  | OLC Admin site lets you search the asset archive and view the contents
344 | 2 | Message Bus | ArchivePreviewService | 8 |  | Create an ArchivePreviewService which subscribes to "New Asset" messages from intranet DMS systems via the bus | [7 empty] | 8
345 | 2 | AssetArchive API | ArchivePreviewService | 4 |  | When the ArchivePreviewService receives "New Asset" messages, it should call the AssetArchive to keep it up to date. | [7 empty] | 4
208.1 | 2 | OLC UI | Styling | 6 |  | Refactor security / membership controls to remove use of tables
208.2 | 2 | OLC UI | Styling | 6 | Kellie's work | Tidy the homepage, master pages, navigator style, quick search, footer etc
208.3 | 2 | OLC UI | Styling | 4 | Kellie's work | Tidy the programme page style
208.4 | 2 | OLC UI | Styling | 4 | Kellie's work | Hovering Preview and Favourites icons
207.1 | 2 | Team | CI | 4 |  | CI Builds OLC & all developers can manual deploy
207.2 | 2 | Team | CI | 4 |  | CI Builds AssetArchive.Service & all developers can manually deploy | [7 empty] | 4
207.3 | 2 | Team | CI | 4 |  | CI Builds AssetArchive.ProcessService & all developers can manually deploy | [7 empty] | 4
| 2 |  |  | 81
321 | 3 | OLC UI | Bug Fixes |  | Bugs | Fix any bugs introduced in iteration #1
324 | 3 | Subsystem Facades | Quality Assurance | 5 |  | Retrofit Unit-Tests to functionality introduced in iteration #1
343 | 3 | OLC UI | Messaging | 13 |  | Message bus passes StoreAsset message from PreviewService to AssetArchiveService so that messages from PreviewService result in the Programme Page's 'has preview' icon changing
303 | 3 | Message Bus | Preview | 13 |  | Build a PreviewService which will eventually wrap DCS / OLC2 preview file management, and publish "New Asset" messages to the bus | [7 empty] | 13
332 | 3 | OLC UI | Quality Assurance | 5 | IE6, Safari | Test / Fix styling for all supported browsers
315 | 3 | Team |  | 8 | Kellie's work | Story-board the OLC Admin site's screen flow and layout
137 | 3 | OLC UI | Quality Assurance | 3 |  | System errors should be handled gracefully and logged for easy review / debugging
| 3 |  |  | 47
330 | 4 | Messaging SubSystem Interface | Programme Image | 5 |  | WAM commands call a messaging subsystem when a programme image is saved
331 | 4 | Messaging SubSystem Interface | Programme Image | 13 |  | Provide a messaging subsystem in WAM to send new asset messages to the bus
333 | 4 | Team | Messaging | 3 |  | Allow easy tracking of message paths through the system
335 | 4 | MarketingCatalogue SubSystem Interface | Programme Image | 5 |  | Provide a MarketingCatalogue subsystem in WAM so that the web form can be populated with MarketingCatalogue items
336 | 4 | AssetArchive.ProcessService | Programme Image | 3 |  | Message bus passes 'store asset' messages from WAM to the AAPS | [7 empty] | 3
337 | 4 | Team | Programme Image | 2 |  | Fake CDN
338 | 4 | Subsystem Facades | Programme Image | 5 |  | AAPS co-ordinates calls to AAS and AssetCopier subsystem | [7 empty] | 5
339 | 4 | AssetArchive.ProcessService | Programme Image | 3 |  | Provide an asset copier subsystem for the AAPS which copes assets from the DMS to (fake) CDN
340 | 4 | AssetArchiveService | Programme Image | 8 |  | Upgrade the AAS to support MCI as metadata for an asset | [7 empty] | 8
341 | 4 | OLC AssetArchive SubSystem | Programme Image | 2 |  | AAS provides a web service to retrieve asset(s) URLs for a MCI | [7 empty] | 2
342 | 4 | OLC UI | Programme Image | 1 |  | Programme page displays image as returned from AAS web service call
205 | 4 | Team | Get ready for WAM | 13 |  | Integrate WAM and CCI into a single C# project so that WAM development uses the same structure as the other OLC applications
322 | 4 | Team | Messaging | 5 |  | Get DCS 1.5 building and running in 'systest one' so that we can test our messaging code through it
| 4 |  |  | 68
48 | 5 | OLC UI | Preview Player | 5 | 11.7 | As a logged in user viewing a programme page, I want to see a paged list of previews (episodes) related to the current MarketingCatalogueItem that I have active permissions on, along with the date the permission is set to expire
49 | 5 | OLC UI | Preview Player | 3 | 11.7 | As a logged in user viewing preview content, I want to click on one of the episodes in the list and have it play within the page
50 | 5 | OLC UI | Preview Player | 3 | 11.7 | As a logged in user viewing preview content, I want a link from each item in the list, to open the clip in my default media player client
327 | 5 | OLC UI | Preview | 3 | 11.7 | Build a skeleton preview page
334 | 5 | WAM UI | Programme Image | 5 |  | WAM 'attach picture' web form calls the commands to save the asset and send a message to OLC
308 | 5 | After-Sales | After-Sales Assets | 8 |  | If a Photo (which relates to an Episode of a SKU) is added via WAM, it should be uploaded to CDN immediately if any clients have after-sales permissions on its parent SKU so that they can download it from their after-sales area
27 | 5 | OLC UI | Client Registration | 5 | 2.1 | As a Client of the BBC, I want to be able to register with the OLC so that, once my application has been activated by a BBC staff member, I can start using the site
30 | 5 | Admin UI | Client Registration | 1 | 2.3 | As a Client of the BBC who has registered but not yet been activated, I want to be informed that my account is not yet activated if I attempt to log in
352 | 5 | OLC UI | Client Registration | 2 |  | Fix update profile to handle client users
348 | 5 | Team |  | 5 |  | Clean all references to Skelta / immediacy out of WAM UI and call subsystems instead
350 | 5 | OLC UI |  | 2 |  | Consistent Catalogue Item Ids from WAM - OLC
347 | 5 | OLC UI |  | 3 |  | Implement standardised validation
96 | 5 | Admin UI | Admin | 5 | 7.2 | As a user admin, I want to be able to search the database of users using various attributes so that I can perform operations on that user such as email, maintain profile, grant after-sales
99.1 | 5 | Admin UI | Admin | 1 | 7.5 | As a user admin, I want to be able to change attributes in the staff user's profile
99.2 | 5 | Admin UI | Admin | 2 | 7.11 | As a user admin, I want to be able to change attributes in the client user's profile
105.1 | 5 | Admin UI | Client Registration | 1 | 7.5 | As an admin, I want to be able to activate the account of a staff user who has registered
105.2 | 5 | Admin UI | Client Registration | 2 | 7.11 | As an admin, I want to be able to activate the account of a client user who has registered
316 | 5 | Admin UI | Get ready for Admin | 8 | 7.1 | Create basic CSS layout framework for OLC Admin site
64
351 | 6 | Team |  | 3 |  | Investigate and document task of integrating with Discus
94 | 6 | Admin UI | Admin | 5 | 7.7 | As a user admin, I want to be able to maintain static data lists used in user-registration forms on the site (e.g. Title, Role, Sales Team, JV channel)
95 | 6 | Admin UI | Admin | 5 | 7.5 and 2.2 and 2.1 | As a user admin, I want to be able to map a sales team to country or sales format, so that each user who registers is assigned a sales team.
101 | 6 | Admin UI | Emails | 5 | 7.9 | As a user admin, I want to be able to edit the signature that will be automatically sent when the system sends emails on my behalf
117 | 6 | OLC UI | Preview | 5 | 2.7 | As a view-by-request user, the Programme Page will allow me to request online viewing of preview materials where available. The admin should be emailed to let them know that I have requested access to this preview
116 | 6 | Admin UI | Preview | 13 | 2.7 | As a sales rep, I want to be notified when a view-by-request user asks for online preview permission, and be able to grant that user permission on preview content where appropriate so that the user can watch it online
305 | 6 | Admin UI | Preview | 8 | 7.6 | A Sales Person using the OLC Admin interface needs to be able to force Preview Clips to be uploaded to the CDN (and the archive consequently updated) so they can be watched from the OLC
353 | 6 | OLC UI | Preview | 3 | 11.7 | As a user I should only be able to see preview clips that I have active permission for
98 | 6 | Admin UI | Admin | 3 | 7.4 | As a user admin, I want to be able to delete user's OLC account |  |  | Medium | Low | 2007-04-13
50
407 | 7 | OLC After-Sales UI |  | 1 | 5.1 to 5.4 | Very simple after-sales page showing the list of SKUs that a user has permissions on, and the date they are set to expire
408 | 7 | WAM UI | un-publish / replace asset | 5 |  | As a WAM user, I want to be able to delete an asset from OLC / CDN by setting complete = false
410 | 7 | Admin UI | Delete user | 1 | 7.4 | Delete SSO record when a user is deleted via the Admin UI
409 | 7 | WAM UI | un-publish / replace asset | 3 |  | As a WAM user, I want to be able to replace an existing asset and see the new Asset on the OLC
354 | 7 | Admin UI | After-Sales Admin | 8 | 7.8 | As an after-sales admin, I want to be able to search for a client who has purchased a programme, and grant them after-sales permission for a SKU so that they will be able to access the after-sales assets for that SKU for a set period of time User should get an email
400 | 7 | Email | Preview: Send Email | 5 | 7.6 | When a customer is granted access to a preview clip, only send them an email if the clip exists on CDN, otherwise start a copy process and send the email once the copy is complete
323 | 7 | Admin UI | Preview | 3 | 8.4 | As a sales person, I want to be able to search for a client to identify the preview clips they have permissions on (still to be properly defined)
103 | 7 | Admin UI | After-Sales Permissions | 2 | 7.8 | As an after-sales admin, I want to be able to view the list of SKUs that a client user has after-sales permissions on
403 | 7 | Admin UI | Send Email Validation | 3 | 7.6 | As an admin attempting to send an email, checks should be made when I hit 'Send' to validate my input against business rules
404 | 7 | Admin UI | Admin Styling | 5 | Kellie's work | Admin screens should look like the mock-ups
405 | 7 | Admin UI |  | 1 | Kellie's work | Preview analysis and mock-ups after searching, granting permissions etc
406 | 7 | Admin UI |  | 3 | Kellie's work | After-sales admin analysis and screen mock-ups
349 | 7 | Team |  | 3 | ?every iteration | CI for Admin site |  |  | Low | High | 2007-04-13
414 | 7 | Team | Demo | 2 | ?every iteration | Get a good, slick demo ready
45
309.1 | 8 | Team | Integrate with Discus | 3 |  | Research and Design Discus Service |  |  |  |  | 2007-04-19 |  |  | 3
309.2 | 8 | Discus Service | Integrate with Discus | 8 |  | Discus Service, responding to a ping from the Task Scheduler, checks for any new Assets in Discus and sends any required StoreAsset messages to the Bus. |  |  |  |  | 2007-04-19 |  |  | 8
309.3 | 8 | AA Process Service | Integrate with Discus | 3 |  | Extend Task Scheduler to call the Discus Service |  |  |  |  | 2007-04-19 |  |  | 3
309.4 | 8 | Team | Integrate with Discus | 5 |  | CI / deploy script for Discus Service |  |  |  |  | 2007-04-19 |  |  | 5
309.5 | 8 | CDN | Integrate with Discus | 8 |  | Process Service can copy assets from Discus to CDN |  |  |  |  | 2007-04-19 |  |  | 8
309.6 | 8 | CDN | Integrate with Discus | 5 |  | Process Service can decide whether After-Sales Assets should be copied to CDN or not |  |  |  |  | 2007-04-19 |  |  | 5
396 | 8 | Admin UI | After-Sales Admin | 3 | 8.4, 7.8 | As after-sales admin, I want to be able to remove a particular client user's access to a particular SKU
57 | 8 | OLC UI | Preview | 5 | 17.3 | As a logged in user viewing any page on the site, I want to be able to access a list of preview content that I have permission on and navigate to the preview section of the relevant programme so that I can view that clip
148 | 8 | OLC UI | Favourites | 3 | 17.2 | Fancy rollover Favourites Viewer with remove favourite functionality, excluding advanced favourites function (see 424)
419 | 8 | After Sales | After sales assets | 5 |  | When a SKU-related asset (i.e. episode photos which are after sales assets) is added to WAM then it should only be copied onto the CDN if a user has permission to view it. |  |  |  |  | 2007-04-19
71 | 8 | OLC UI | Favourites | 1 | 10.3 | As a logged in user viewing the homepage, I want to see the last three programmes I added to my favourites be displayed as links to the programme page |  |  |  |  | 2007-04-24
403.1 | 8 | Admin UI | Send Email Validation | 1 |  | Carried over 1 point from 403 not completed in iteration 7 : As an admin attempting to send an email, checks should be made when I hit 'Send' to validate my input against business rules
404.1 | 8 | Admin UI | Admin Styling | 3 | Kellie's work | Carried over 3 points from 404 not completed in iteration 7 reduced to 3 days. Admin screens should look like the mock-ups
53
63.1 | 9 | OLC UI | After-Sales Permissions | 1 | 10.5 and 18.3 | As a logged in client user, I want to see a link from the home page to the After-Sales area of the site styled depending on whether I have none/some/new after sales items |  |  |  |  | 2007-04-24
41 | 9 | OLC UI | Electronic Press Kit | 5 | 11.5 | Links to movie clips in the Electronic Press Kit will be displayed, and if clicked will run the movie in the window in the same area as the promo clip. |  |  | Medium | Low | 2007-04-13
372 | 9 | OLC UI | Electronic Press Kit | 2 | 11.5 | As a user I want to be able to expand and collapse the Electronic Press Kit group of assets, and not see the link if there are no assets |  |  |  |  | 2007-04-24
40 | 9 | OLC UI | Marketing Materials | 5 | 11.5 | For each MarketingCatalogueItem, links to any Marketing Materials assets that exist in WAM (Info Sheet, Episode Synopsis, Ratings and Reviews, Awards) will be displayed |  |  |  |  | 2007-04-24
387 | 9 | OLC UI | Marketing Materials | 3 | 11.5 | Colour Brochure link will display one of three AssetTypes using a rule to determine which takes precedence. |  |  |  |  | 2007-04-24
371 | 9 | OLC UI | Programme page | 1 | 11.3 | As a user I only want to see the Marketing Materials tab if there are marketing material assets available for that MCI |  |  |  |  | 2007-04-24
379 | 9 | OLC UI | various pages |  | 21.1 | As a user I want to see all pdfs open in a pdf viewer if that is available on the user's PC |  |  |  |  | 2007-04-25
53.1 | 9 | OLC UI | Preview Player | 1 | 11.7 | As a logged in user viewing preview content, I want an improved behaviour in that the chosen preview clip will continue playing when I browse the list of available preview clips for that MCI |  |  |  |  | 2007-04-24
325.1 | 9 | OLC UI | Preview | 5 | 11.7 | When two resolutions of a preview clip are available, allow the user to choose which to display |  |  |  |  | 2007-04-24
325.2 | 9 | OLC UI | Preview | 5 |  | When a new preview clip arrives at the preview service, two versions (low re and High re) should be stored in the asset archive and be copied together to the CDN when permission is granted
439 | 9 | OLC UI | Programme page | 2 |  | As a user I want to see programme pages coloured in accordance with the primary marketing genre. If there is >1 marketing genre choose the first in the list.
87.1 | 9 | OLC UI | System Check | 1 | 3.1 | As an unregistered or non-logged-in user, if I try to view any page on the OLC site, but I do not have a supported browser I will not be logged in and will be redirected to a page that offers information |  |  |  |  | 2007-04-25
328 | 10 | OLC UI | Staff Registration | 1 | 2.1 | User registration drop-downs should default to blank values so that the user is forced to pick one and not just blindly accept the default |  |  |  |  | 2007-04-25 | n
355 | 9 | Team | Messaging | 1 |  | Ensure all message bus calls support failover - i.e. messages are queued if the recipient is unavailable | [7 empty] | 1
329.1 | 9 | OLC UI | Search | 1 |  | The search engine index should be rebuilt every day so that new product data brought in from ORAC by pub/sub can be searched on
417 | 9 | AssetArchive Process Service API |  | 3 |  | Implement queuing in the copier subsystem so that big files don't hold OLC3 up |  |  |  |  | 2007-04-18 |  |  | 3
37
325.3 | 10 | OLC UI | Preview | 3 | 11.7 | As a client I want my High/Low preview resolution preference to be stored in my profile (and editable from the preview tab) | [5 empty] | y
302 | 10 | PreviewService API | Preview | 5 |  | Integrate PreviewService with OLC2's existing Asset Management code so that it can run side-by-side and detect new assets shipped from DCS | [5 empty] | y |  | 5
72 | 10 | OLC UI | Preview | 3 | 10.4 | As a logged in client user with at least one Preview Permission viewing the homepage, I want to see the titles of the last three programmes on which I was given preview permissions displayed as hyperlinks to the preview section of the relevant programme page so that I can easily return to those previews (Obviously only display those previews that I still have permission on.) |  |  |  |  | 2007-04-24 | n
399 | 10 | OLC UI | Preview | 8 | 2.7 | As a view-direct user, the Programme Page will allow me to request online viewing of preview materials where available. My request should be logged by the system and automatically processed within a few minutes so that I get an email and can then watch all of the available previews for that MCI, for the default number of days (currently 90). I will receive a confirmation email when the previews are available on the CDN. An email will be sent to my sales team for info to tell them I am watching these previews. |  | SA | Low | High | 2007-04-13 | n
39 | 10 | OLC UI | Content Management | 5 | 11.5 | If a Promo Clip exists (in WAM) for the MarketingCatalogueItem it will be displayed within the page and allow the user to play it |  |  |  |  | 2007-04-24 | n
42 | 10 | OLC UI | Electronic Press Kit | 1 | 11.5 | If an electronic press kit clip has been watched in the player, a link to show the promo clip again will be displayed |  |  |  |  | 2007-04-24 | n
19 | 10 | OLC UI | Preview Data Migration | 5 | Delivery | Migrate data from PreviewService into AssetArchiveService | [5 empty] | y
421 | 10 |  |  | 5 |  | Build and deploy scripts for task scheduler | [5 empty] | y | ?
311 | 10 | OLC UI | Marketing Materials | 3 |  | If a new Asset is added via WAM to the DMS that relates to a MarketingCatalogueItem that has not yet been published to the OLC, nothing needs to happen |  |  |  |  | 2007-04-19 | y | 1
401 | 10 | Admin UI | Saved / Draft Emails | 1 | 7.12 and 7.13 | As an admin, I want to be able to view a list of sent / draft emails |  | SA |  |  | 2007-04-24 | n
39
317.1 | 11 | OLC UI | Messaging | 4 | 1.8 | Get pub / sub running from ORAC - OLC so that the OLC updates when ORAC product data is changed |  |  |  |  | 2007-04-25 | y
444 | 11 | OLC UI | Electronic Press Kit | 5 | 11.5 | As a user I want to see the name of the EPK clip (setup in WAM) in the dropdown list that appears on the marketing materials tab. | [5 empty] | y
320 | 11 | OLC UI | Messaging | 3 | 1.8 | Get pub / sub running from WAM MarketingCatalogue - OLC so that the OLC is updated when marketing catalogue data is changed via WAM UI | [5 empty] | y
383.1 | 11 | Admin UI | Preview | 8 | 7.31 | As an admin user, I want to search for and view all previews that exist on the intranet (hi-res version), searching by MarketingCatalogueItem |  | SA |  |  | 2007-04-25 | y
83.5 | 11 | OLC UI | News Items | 5 | 12.1 | As an OLC user, I want to see the relevant list of programme-related news items when viewing the news page or a genre homepage | [5 empty] | n
319 | 11 | WAM | Messaging | 3 | 1.8 | Get pub / sub running from ORAC - WAM MarketingCatalogue (formerly CCI) so that changes in ORAC are immediately seen in WAM (CCI/WAM pub/sub works but needs to be made to work in the new WAM CCI structure) | [5 empty] | y | 3
378 | 11 | OLC UI | Themed Promotions | 8 | 16.1 | As a user I want a link on the homepage which takes me to a page that lists Themed Promotion PDF documents (content managed in CMS) | [5 empty] | n
113 | 11 | OLC UI | Security | 8 | Delivery | A repeatable script that migrates all existing OLC2 users accounts to OLC3's user database(s) | [5 empty] | n
329.2 | 11 | OLC UI | Search | 2 |  | The task scheduler fires the search engine indexing regularly, (so that the search engine index should be rebuilt every day so that new product data brought in from ORAC by pub/sub can be searched on) |  | NA |  |  |  | y | 2
46
402.1 | 12 | Admin UI | Saved / Draft Emails | 2 | 7.22/7.33 | As an admin, in the Pre-sales area I want to be able to reopen a sent / draft email for re-use |  | NA |  |  | 2007-06-12 | n
420.1 | 12 | Admin UI | Preview | 2 | 7.20/7.21 | As an admin, I want to be able to grant access by email to MCIs. This is to amend the existing functionality |  | NA |  |  | 2007-06-12 | n
420.2 | 12 | Admin UI | Preview | 3 | 7.20/7.21 | As an admin, I want to be able to grant access by email to previews. This is to amend the existing functionality |  |  |  |  | 2007-06-12
447 | 12 | Admin UI | After-Sales Admin | 2 | 7.24 | As after-sales admin, I want to be able to edit the signature that will be automatically sent when the system sends emails on my behalf. Modified functionality to include text editing facility |  | NA |  |  | 2007-06-12
365 | 12 | Admin UI | Admin | 1 | 7.5 | As part of an admin user making an inactive client user active, an email must be sent to the user telling them they have been activated |  | NA | Medium | Low | 2007-04-25 | n
430 | 12 | OLC UI | Preview Data Migration | 8 | Delivery | a repeatable script that migrates all existing OLC2 preview permissions to create tokens, by extending and re-running the user migration script |  |  |  |  | 2007-06-14 | n
19 | 12 | OLC UI | Preview Data Migration | 3 | Delivery | Re-run the preview Migration script in part as a pilot to test the results and predict the volumes required. To be used to decide whether real Akamai CDN needs to be used for storing the previews | [5 empty] | n
422 | 12 |  | Delivery | 3 | Delivery | Parameterise configuration settings for deployment to systest/UAT/live environments |  | NA |  |  | 2007-04-20 | n
475.1 | 12 |  |  | 3 |  | First part of Set up the new sys test environment
377.1 | 12 | OLC UI | Search HD | 2 | 14.1 | As a user when I click the HD link on a programme page, or on the home page, I want to see search results of all programme with HD content, | [5 empty] | n
476 | 12 |  |  | 3 |  | Change the build scripts to web application projects
317.2 | 12 | OLC UI | Messaging | 2 | 1.8 | Complete the pub / sub running from ORAC - OLC so that the OLC updates when ORAC product data is changed
34
130.1 | 13 | OLC UI | Emails | 2 |  | Preparing to set up generic email templates in OLC |  | NA |  |  | 2007-07-12 | n
381.2 | 13 | OLC UI | Print Catalogue | 1 | 10.6 | As an OLC user, I want to see the list of print catalogues as uploaded in the CMS displayed on the homepage | [5 empty] | n
78 | 13 | OLC UI | Content Management | 3 | 10.8, 10.9 | As a logged in user viewing the homepage, I want a link to Quarterly Highlights and Digital media PDF documents (Note "Trade markets" was once "Events and Press" | [5 empty] | n
474 |  | OLC UI | News Items | 1 |  | As a user I want to be able to click a link at the foot of each genre page so that I am taken to an advanced search results page, having selected all programmes which are for that genre. |  | NA
471 | 13 | OLC UI | Advanced Search | 3 |  | As a user I want to be able to search by sub-genre as well as marketing genre.
110.1 |  | WAM CMS UI | Themed Promotions | 2 | 6.4 and 6.5 | As a developer, I want to be able to create / edit / delete a list of Themed Promotions, each of which has an associated PDF document using a Times new Roman screen |  | NA |  |  | 2007-06-14
151 | 13 | OLC UI | Search | 3 | 1.4 | User refines the free-text search by specifying a SubGenre of the Marketing Genre from a list which is re-loaded using AJAX when the Marketing Genre is changed | [5 empty] | n
15
130.2 | 14 | OLC UI | Emails | 2 |  | Preparing to set up generic emails in OLC Admin |  | NA |  |  | 2007-07-12 | n
448 | 14 | Admin UI | After-Sales Admin | 5 | 7.26 | As after-sales admin, I want to be able to search for a client who has purchased a programme, and grant them after-sales permission for a SKU so that they will be able to access the after-sales assets for that SKU for a set period of time. User should get an email. |  | NA |  |  | 2007-06-12
402.2 | 14 | Admin UI | Saved / Draft Emails | 1 | 7.28/7.29 | As an admin, in the After sales area I want to be able to see a list of sent/draft mails and reopen a sent / draft email for re-use |  | NA |  |  | 2007-06-12 | n
90.1a | 14 | OLC After-Sales UI | After-Sales | 1 | 5.1 to 5.4 | As a client of BBCWW who has purchased a SKU and been granted access by and admin, I want to be able to view the list of after-sales assets that I have permission on. Excluding the grouping of photo assets |  | SA | Low | Low | 2007-04-13 | n
90.2 | 14 | OLC After-Sales UI | After-Sales | 3 | 5.1 to 5.4 | As a client of BBCWW who is viewing their after-sales assets, I want to be able to filter and sort the view |  | SA | Low | Low | 2007-04-13 | n
208.5 | 14 | OLC UI | Search results | 5 | Conditions of Satisfaction Doc | As a user of the OLC, I want to be able to search the catalogue quickly and easily so that I can find programmes that I am interested in. |  | BA | High | Low | 2007-04-24 | n
90.6 | 14 | OLC After-Sales UI | After-Sales Thumbnail | 3 | 5.1 to 5.4 | As a client of BBCWW who is viewing their after-sales assets, I want all photograph assets to be displayed with a thumbnail Breakdown into two features 1 for display and 2 for integration with WAM |  | SA | Low | Medium | 2007-04-13 | n
90.3 | 14 | OLC After-Sales UI | After-Sales | 3 | 5.1 to 5.4 | As a client of BBCWW who is viewing their after-sales assets, I want to be able to select some or all of those assets |  | SA | Low | Low | 2007-04-13 | n
90.8 | 14 | OLC After-Sales UI | After-Sales | 1 | 5.1 to 5.4 | As a client of BBCWW who is viewing their after-sales assets, I want to be able to open a caption list or a photo and view them before I download them. |  |  |  |  | 2007-07-17
63.2 | 14 | OLC UI | After-Sales Permissions | 1 | 10.5 and 18.3 | As a logged in client user, I want to see a link from the left hand menu on every page to the After-Sales area of the site styled depending on whether I have none/some/new after sales items |  | NA |  |  | 2007-04-24
|  |  |  | 25 |  | at 1fp per day this target would be 23
448.2 | 15 | OLC UI | After sales | 1 |  | As a user of the client after sale pages, I want to see an improved interaction and layout.
90.1b | 15 | OLC After-Sales UI | After-Sales | 2 | 5.1 to 5.4 | As a client of BBCWW who has purchased a SKU and been granted access by and admin, I want to be able to view the list of after-sales assets that I have permission on, with the grouping of photo assets |  | SA | Low | Low | 2007-04-13 | n
477 | 15 | OLC UI | Emails | 2 |  | As a user I want emails being sent on behalf of UK sales teams to be sent with a company registration message. Emails sent by Worldwide staff based in the UK will contain the registration details, non-UK Worldwide staff will not have any. For wording please see Ian Briggs |  | NA |  |  | 2007-07-17
130.3 | 15 | OLC UI | Emails | 5 |  | All system emails should be produced using generic template system to allow html formats and to allow email signatures to have bold etc. Includes the reply to address being intvwebmaster@bbc.co.uk (see bug 339) |  | NA |  |  | 2007-07-12 | n
83.6 | 15 | OLC UI | News Items | 5 | 12.1 | As an OLC user, I want to see the relevant list of non-programme-related news items when viewing the news page or genre homepages |  | NA |  |  | 2007-06-12 | n
217 | 15 | OLC UI | Registration | 5 | 2.1 | As a client registering and amending my profile, I want to be able to click a joint venture partner checkbox and to have a rollover tip which explains what this means. I also want the table of broadcast territories to have the JV email address in it as per the table in the use case. |  |  |  |  | 2007-07-17
480 | 15 | OLC Admin | User search | 2 |  | As a user I want to be able to search for a user by their email address as well as by their name |  | SA |  |  | 2007-07-17
118 | 15 | OLC UI | Preview | 1 | 11.2 | As a client, I want the Programme page header section to allow me to order a DVD of preview materials where available |  | NA |  |  | 2007-04-24 | n
481 | 15 | OLC UI | Programme Page | 2 |  | As a staff user, when I click on the View Materials icon I want to see a message saying there are DVDs and/or previews available |  | NA |  |  | 2007-07-17
|  |  |  | 25 |  | Initial target 27. At 1fp per day this target would be 29 (less the 5 that Stephen is doing on WAM) = 24
433 | 16 | OLC UI | After sales migration | 5 | Delivery | a repeatable script that migrates all existing OLC2 after sales permissions (SKU Tokens) | [5 empty] | n
434 | 16 | OLC UI | After sales migration | 5 | Delivery | a repeatable script that migrates all existing OLC2 after sales data (episode photos, caption lists) in accordance with the permissions | [5 empty] | n
440 | 16 | OLC UI | Registration | 3 | from bug 323 | as a user signing up via the internet as a staff user, my account should not be activated immediately. I want to receive an email with a hyperlink to an intranet page that activates my account, so that the site verifies that I am really a staff user." (note that we need to be sure that all 'staff users' will be able to access this intranet activation page) also fix bug 1242 at the same time |  | NA |  |  | 2007-05-10 | n
441 | 16 | OLC UI | Registration | 2 | from bug 323 | "as a user signing up via the internet, I want the site to ask for details both to staff and client users first, then based on those answers ask me the appropriate set of questions next, so that I don't have to explicitly choose whether I'm signing up as a staff or client user" |  | NA |  |  | 2007-05-10 | n
93 | 16 | Admin UI | Admin | 5 | 7.1 | As a user admin, I want to be able to register a staff user as a user of the OLC so that they can immediately start using the site (includes sending them an email) |  | NA |  |  |  | n
218 | 16 | OLC Admin | User admin | 1 | 7.5 | As an admin I want to be able to view and change a joint venture partner checkbox on client profiles |  |  |  |  | 2007-07-17
|  |  |  | 21 |  | Target in plan of 20 to 24 based on 20 days available i.e. plan shows 20 at 1FP per day (note SK 5 on WAM)
478 | 17 | OLC UI | Emails | 2 |  | As an admin user receiving an email from OLC to register a client, or to grant access to previews, I want to have a link on the email to take me to the appropriate page in OLC Admin so that I can carry out the task. |  | NA |  |  | 2007-07-17
429.1 | 17 | OLC UI | Primary Marketing Genres | 5 |  | As a user I want to see Primary Marketing genres, which have been defined in WAM, - i.e. when viewing the programme page, I want to see the primary marketing genre and an appropriately styled list of other marketing genres which apply to that MCI. When no PMG is defined, I want to see the programme page styled in a neutral (i.e. non-genre) colour |  | NA |  |  | 2007-04-25 | y | 3
75 | 17 | OLC UI | New to Preview | 8 | 10.1 and 15.1 | As a logged in user viewing the homepage, I want a link to a page which lists new preview content so that I can check for ones I am interested in and potentially request them. Most recently added displayed first listed by episode, rather than by programme |  | NA |  |  | 2007-04-24 | n
219 | 17 | OLC Admin | System Admin | 2 | 7.7 dropped | Original feature now dropped, so as a user I no longer want this to be available..... As an admin user I no longer want to be able to amend the systems' picklists. These picklists should be available for developers only, as they should not be altered by users without some additional work users could not do. In addition as developer, I only want to have .bbc.co.uk in the staff email picklist. |  |  |  |  | 2007-07-17
| 17 | OLC UI | User registration | 3 |  | Paul's handover and improvements to user registration (actually 4 days this week) |  | NA
|  |  |  | 21 |  | Target in plan should be 20 based on 20 days available i.e. plan shows 20 at 1FP per day
216 | 18 |  | DCS Preview service | 5 |  | Amend DCS integration (formerly known as version 1.5) to cope with DCS2 project which has created DCS v2.0. Matt's email of 11 July specifies |  |  |  |  | 2007-07-17
5
109.2 | 21B | OLC UI | Genre Banner | 2 | 12.1 | As an OLC user, I want to see one of the genre banners uploaded by the content admin displayed at the top of the news & ratings page. If more than one banner in CMS, should rotate on each page request. |  | SA |  |  |  | n
109.1 |  | OLC UI | Genre Banner | 3 | 12.1 | As an OLC user, I want to see one of the genre banners uploaded by the content admin displayed at the top of the genre homepage. If more than one banner in CMS, should rotate on each page request. |  | SA |  |  |  | n
361 | 21B | OLC UI | Programme pages | 1 |  | As a user of OLC I only want to see programmes that are active based on the ORAC AND WAM "active" business rules |  | NA |  |  | 2007-04-25 | y | 1
500.1 | 21B |  | refactoring | 3 |  | refactoring as needed for iteration 21
9
87.2 | 22 | OLC UI | System Check | 1 | 3.1 | As an unregistered or non-logged-in user, I want to see information telling me what software the site uses so that I can consider whether to download it. (this would for instance include a pdf reader, powerpoint slides and Flash) |  | NA |  |  | 2007-04-25
429.2 | 22 | OLC UI | Primary Marketing Genres | 1 |  | As a user I want to see Primary Marketing genres published from WAM |  | NA |  |  | 2007-04-25 | y | 3
73 | 22 | OLC UI | Featured Programme | 8 | 10.2 | As a logged in user viewing the homepage, I want to see a Featured Programme Box in prime position on the homepage, showing animated content and hyperlinking to that programme. |  | SA |  |  |  | n
362 | 22 | OLC Admin | Security/Access control | 13 | 3.3 | As a user I am only allowed to carry out certain functions,. Those I am not allowed to do should not be visible to me. |  | SA |  |  | 2007-04-25 | n
44 | 22 | OLC UI | Marketing Materials | 3 | 11.5 | As a user I want to see useful web links relevant to the MarketingCatalogueItem displayed on the Marketing Materials Section and when I click on them they open in a new window |  | NA |  |  | 2007-04-25 | y | 1
472 | 22 | OLC UI | Programme Page header | 1 | 11.2 | As a user I want to see a message saying whether the Programme (MCI) is "Available now" or "Coming soon" |  | NA
216.1 | 22 | All components | Integration of OLC3 components | 5 |  | Amend first part of Active MQ (see also 216.2) |  |  |  |  | 2007-07-17
631.2 | 22 | WAM UI | WAM photos | 5 | WAM 2.3 | rest of bulk photo upload
500.2 | 22 | OLC UI | refactoring | 8 |  | refactoring as needed for iterations 23 onwards
note for self (193 + 16 = 209) at start of iteration 22
|  |  |  | 42 |  | deducted 3 points in total as carried forward to next iteration
389.1 | 23 | Team | UAT Release | 3 | Delivery | First release to UAT (to be done component by component) | [5 empty] | n
389.2 | 23 |  | UAT Release | 5 | Delivery | Deploy Discus service
385.1 | 23 | CDN | CDN |  | Delivery | Create UAT and Production environments for CDN within Akamai only 4 hours done |  | SA |  |  |  | y | 5 | 0
313.1 | 23 | OLC UI | Marketing Materials | 3 |  | If a MarketingCatalogueItem is moved from 'unpublished' to 'published' state in WAM, all related assets in the WAM DMS should be uploaded (or have already been uploaded) to the CDN so that clients can see them via the OLC |  | NA |  |  | 2007-04-25 | y | 3
429.3 | 23 | OLC UI | Primary Marketing Genres | 5 |  | Complete the feature: As a user I want to see Primary Marketing genres published from WAM |  | NA |  |  | 2007-04-25 | y | 3
216.2 | 23 |  | Integration of OLC3 components | 5 | Delivery | Amend rest of Active MQ (see also 216.1) |  |  |  |  | 2007-07-17
216.2.1 | 23 |  | Integration of OLC3 components | 2 | Delivery | AAPS (10)
216.2.3 | 23 |  | Integration of OLC3 components | 1 | Delivery | Discus (only half done. Rest in i24)
c/f from i22 | 23 |  |  | 3 |  | 472 = 2 hours, 44 = 2 hours, 362 = 11 hours, 631 = 4 hours TOTAL 19hours = 3 points c/f from iteration 22
27
385.2 | 24 |  | CDN integration | 5 | Delivery | Create UAT and Production environments for CDN within Akamai - 4 hours out of 30 (=5 pts) done in i23
216.2.4a | 24 |  | Preview integration | 7 | Delivery | Preview service to use Active MQ
44.2 | 24 |  | weblinks integration | 1 |  | Sending weblinks from WAM to OLC3
230 | 24 |  | OLC admin integration | 2 |  | ORAC product to OLC admin
231 | 24 |  | OLC admin integration | 8 |  | WAM MCIs to OLC Admin
234.1 | 24 |  | OLC searching index | 1 |  | Ensure search index is rebuilt when new MCIs arrive in OLC
235 | 24 |  | Preview integration | 1 |  | Adapt preview service to cope with firewall arrangements
236 | 24 |  | UAT Release | 3 |  | MQ broker internal / external bridge
237 | 24 |  | UAT Release | 1 |  | Release OLC admin to UAT
238 | 24 |  | UAT Release | 2 |  | NANT packager
252 | 24 |  | UAT Release | 2 |  | Release OLC to UAT
253 | 24 |  | UAT Release | 3 |  | Release Asset archive service to UAT
255 | 24 |  | UAT Release | 2 |  | Automate publishing in UAT (i.e. task scheduler and messages)
38
216.2.4b | 25 / 26 |  | Preview integration | 1 |  | Preview service to use Active MQ
234.2 | 25 / 26 |  | OLC searching index | 1 |  | Ensure search index is rebuilt when new MCIs arrive in OLC
232 | 25 / 26 |  | OLC admin integration | 2 |  | WAM genres to OLC admin
256 | 25 / 26 |  | UAT Release | 3 |  | Release Preview Service to UAT
257 | 25 / 26 |  | UAT Release | 3 |  | AAPS should send previews to streaming akamai account
390 | 25 / 26 |  | UAT Release | 5 |  | Second release to UAT | [5 empty] | n
246 | 25 / 26 | Emails | Emails |  |  | Update all email words (zero pints as done by Kerry and Kellie)
247.1 | 25 / 26 |  | Fix Bugs | 5 |  | Fix bugs - roughly one full week of the team
260 | 25 / 26 |  | Messaging | 3 |  | Ensure we know if any services have gone down (heartbeat)
244 | H | OLC UI | Emails | 1 |  | Implement email images on UAT and Live
24
258 | OLC 3.0.0 (beta) "Search" | OLC UI |  | 2 |  | Don’t show marketing genres starting with x on OLC search, or anywhere else | Live
287 | OLC 3.0.0 (beta) "Search" |  |  | 2 |  | Add image thumbnails so they are shown in search results and on after sales pages | Live
291 | OLC 3.0.0 (beta) "Search" |  |  | 3 |  | As live support I want to know as soon as a message listener becomes unresponsive | Live
297 | OLC 3.0.0 (beta) "Search" |  |  | 2 |  | When a product is changed in ORAC that would make MCIs active or inactive, the sercah should reflect that | Live
282 | OLC 3.0.0 (beta) "Search" |  |  | 3 |  | Add content for Home and Genre/News pages to UAT / LIVE | Live
280 | OLC 3.0.0 (beta) "Search" |  |  | 3 |  | SEARCH address bugs and relevance | Live
66 | OLC 3.0.0 (beta) "Search" | OLC UI | Footer Links | 1 | 19.1 | As a logged in user viewing any page on the site, I want to see a standard page footer containing links to 'terms and conditions', 'privacy policy', 'contact us', 'help' static html pages | Live | BA |  |  | 2007-04-25 | n
391.1 | OLC 3.0.0 (beta) "Search" |  | Production release | 0 |  | release External Broker | Live
391.2 | OLC 3.0.0 (beta) "Search" |  | Production release | 1 |  | Release OLC | Live
391.3 | OLC 3.0.0 (beta) "Search" |  | Production release | 2 |  | Release OLC Admin | Live
391.4 | OLC 3.0.0 (beta) "Search" |  | Production release | 2 |  | Release OLC AAS and AAPS | Live
281 | OLC 3.0.1 (beta) "Previews" |  |  | 2 |  | optimise the way we use akamai storage | Live
288 | OLC 3.0.1 (beta) "Previews" |  |  | 1 |  | Make sure New to Preview works (feature 75 done in i17) | Live
289 | OLC 3.0.1 (beta) "Previews" |  |  | 1 |  | When an admin grants access to a preview, the file should automatically be copied onto Akamai so that the user can view it | Live
290 | OLC 3.0.1 (beta) "Previews" |  |  | 5 |  | Preview cards (2x3, 3, 2, 2, 4 hours) | Live
283 | OLC 3.0.1 (beta) "Previews" |  |  | 3 |  | Migrate preview metadata into AAS using existing script | Live
391.5 | OLC 3.0.1 (beta) "Previews" |  | Production release | 3 |  | Release Preview Service | Live
294 | OLC 3.0.1 (beta) "Previews" |  |  | 1 |  | As a sales exec I want to be emailed when a view-direct client is granted access to a preview | Live
286.1 | OLC 3.0.1 (beta) "Previews" |  |  | 3 |  | As a user who has access to OLC2, I expect to be able to see the same information in OLC3 | Live | [5 empty] | migrate user & tokens (after-sales too) and spray store-assets messages... Then wait
286.2 | OLC 3.0.1 (beta) "Previews" |  |  | 2 |  | As a user who has previews availlable in OLC2, I expect the same preview to be ready to play as soon as I log in to OLC3 | Live
432 | OLC 3.0.2 (beta) "Showcase" | OLC UI | WAM asset migration | 5 | Delivery | All live pre-sales assets in WAM should be visible on the catalogue - spray StoreAssets msg | Live |  |  |  |  | n
247.2 | OLC 3.0.2 (beta) "Showcase" |  | Fix Bugs | 5 |  | Fix bugs - roughly 25% of a week | Live
226 | OLC 3.0.2 (beta) "Showcase" | OLC UI | Left Hand menus | 2 |  | As a user I want to be able to see and select a link to Formats page, similar to the marketing genre pages, where I can read news items about format programmes. The menu name should be Formats and it should appear after the last marketing genre | Live
699.1 | OLC 3.0.8 (live) "Service Pack" | WAM UI | Contributors | 3 |  | As a user I want to see the results of a one-off migration of the various types of contributor names in ORAC so that appear on the OLC Programme Page under the appropriate headings. i.e. not live updates via messaging | Live
296 | OLC 3.0.2 (beta) "Showcase" |  |  | 2 |  | Review feedback given to users in OLC | Live
Already Done | [12 empty] | Kerry checked outstanding list (14/03/08) and these features have already been done
499 |  | OLC UI | Programme page | 1 |  | As a user I want to see the Duration text from the WAM MCI Duration field and not from the ORAC Version Summary field | Live
220 |  | OLC UI | Preview Materials | 1 | 2.7 | As a user who already has 1 or more previews for an MCI, I want to see a message that says this when I try to request a preview again. I also want to have the view materials menu/popup/dropdown styled in a lovely way. | Live
383.2 |  | Admin UI | Preview | 1 | 7.31 | As an admin user I want to search for and view all previews that exist on the intranet (high-res version), searching by MarketingCatalogueItem so that I can grant access to one or more of them. (Feature 383.1 allowed for the searching and display, this is an addition to add the grant access functionality) Note FP of 1 assumes that grant access has already been built elsewhere | Live | NA
754 |  | WAM |  | 2 |  | As a user attempting to add an asset of a particular type when one already exists on that MCI I want instant feedback and the option to edit/replace the existing asset | Live
215 |  | OLC UI | Preview |  |  | Zero points as only a change to wording on an email template. Change the preview email template wording to reflect the Phase 1 position that newly encoded episodes are not automatically made available to view direct clients. See the Phase 2 feature 214 for the work that will change this. | Live
After sales
295 | OLC 3.0.2.1 (Users and Admin) |  |  | 2 |  | As an admin user I want the admin ui to be clear and usable in the section where we add roles etc. | Live
771 | OLC 3.0.2.1 (Users and Admin) |  |  | 3 |  | As an OLC/OLC Admin user I expect to receive the correct emails with no errors for all functions that create emails | Live
772 | OLC 3.0.2.1 (Users and Admin) |  |  | 2 |  | As an OLC/OLC Admin user I expect the expiry dates on preview to be accurate and no errors to occur | Live
773 | OLC 3.0.2.1 (Users and Admin) |  |  | 2 |  | As an OLC/OLC Admin user I expect all search results to behave as expected | Live
775 | OLC 3.0.2.1 (Users and Admin) |  |  | 2 |  | As an OLC/OLC Admin user registering or updating my details I expect it all to work as it is meant to | UAT
776 | OLC 3.0.2.1 (Users and Admin) |  |  | 3 |  | As an OLC user I expect the search to be elegant, accurate and return clear results | Live
777 | OLC 3.0.2.1 (Users and Admin) |  |  | 2 |  | As an OLC user I don't want to encounter any bugs! | Live
784 | OLC 3.0.2.1 (Users and Admin) |  |  | 3 |  | As an OLC2 user with admin access, I expect to get the same or equivalent privilages when I try to access OLC3's admin site | Live
783 | OLC 3.0.2.1 (Users and Admin) |  |  | 3 |  | Asset Archive - As a user I expect all assets I put into the system to be shown on OLC correctlly | UAT | [5 empty] | new feature since planning
790 | OLC 3.0.2.1 (Users and Admin) |  |  | 1 |  | As a user of OLC Admin, I want the home page to have a summary of what’s available in each section of Admin and links to each of those sections | UAT | [5 empty] | new feature since planning
90.9 | OLC 3.0.3 (beta) "Pre-Sales in After-Sales" | OLC After-Sales UI | After-Sales | 5 | 5.1 to 5.4 | As a OLC2 user with after-sales, I want to be able to search for and download any pre-sales assets (info sheets etc) that are related to the SKU I have purchased | Deleted | SA | Low | Low | 2007-04-13 | n | after-sales tokens have migrated OK
242 | OLC 3.0.3 (beta) "Pre-Sales in After-Sales" | OLC After-Sales UI | After-Sales | 2 |  | After sales breadcrumb to improve navigation | Live
250.1 | OLC 3.0.3 (beta) "Pre-Sales in After-Sales" |  |  | 2 |  | Download zip of all assets in basket | Systest | [5 empty] | was Akamai download manager
250.2 | OLC 3.0.3 (beta) "Pre-Sales in After-Sales" |  |  | 1 |  | User gets feedback while basket is built | Development
250.3 | OLC 3.0.3 (beta) "Pre-Sales in After-Sales" |  |  | 2 |  | Queuing files into/out of basket | Development
250.4 | OLC 3.0.3 (beta) "Pre-Sales in After-Sales" |  |  | 2 |  | Zip file is structured so it makes snese to user | Development
251.1 | OLC 3.0.3 (beta) "Pre-Sales in After-Sales" |  |  | 1 |  | As a client viewing my aftersales area I expect to be able to filter the SKUs by those that are going to expire in the next 30 days and those that have new files in the last 30 days | UAT
251.2 | OLC 3.0.3 (beta) "Pre-Sales in After-Sales" |  |  | 2 |  | As a client on OLC viewing my aftersales section I expect the thumbnail displayed with the SKU to by the right size and link to the assets page for the SKU | UAT
251.3 | OLC 3.0.3 (beta) "Pre-Sales in After-Sales" |  |  | 3 |  | As a client viewing assets for a SKU, I expect it to be quick and easy to find the files I want” | UAT
251.4 | OLC 3.0.3 (beta) "Pre-Sales in After-Sales" |  |  | 2 |  | As a client on OLC viewing my aftersales section I expect to be able to remove SKUs from the list in a satisfactory manner | Waiting for Live
521 | OLC 3.0.3 (beta) "Pre-Sales in After-Sales" |  |  | 1 |  | As an after-sales user who has recently purchased a programme, I expect to be emailed a link to my after-sales area, where I can find pre-sales assets and photos related to that programme | Live | [5 empty] | sku token causes file upload, then email
780 | OLC 3.0.3 (beta) "Pre-Sales in After-Sales" |  |  | 1 |  | After sales bugs | Deleted
785 | OLC 3.0.3 (beta) "Pre-Sales in After-Sales" |  |  | 5 |  | As a OlcAdmin user I want to be able to grant access to aftersales assets for SKUs to OLC users so that they can view aftersales assets on the OLC website” and “As an OLC Admin user I would like the After Sales UI area to be clear, consistent and cleanly designed | Live | [5 empty] | New to Pre Sales
520 | WAM 1.3 (live) "Photos" |  |  | 5 |  | As a wam user I want to be able to store episode photos, generic photos and caption lists, and retrieve them in the same groupings | UAT | [5 empty] | tidy up DMS structure for photos
284 | WAM 1.3 (live) "Photos" |  |  | 3 |  | Migrate photos into WAM: As a WAM user I expect all photo assets from OLC2 to be availlable to me | Development
788 | WAM 1.3 (live) "Photos" |  |  | ? |  | As a Wam user who has browsed to a photo asset so that it can be stored on WAM before selecting the 'genric' or 'episode' options, I expect the system to store the path to the asset so that I do not have to re-browse the asset path after selecting the photo type | Deleted | [5 empty] | Duplicate of 789
789 | WAM 1.3 (live) "Photos" |  |  | 1 |  | As a Wam user I expect all the OLC2 assets to have been migrated properly | UAT | [5 empty] | new feature since planning
794 | WAM 1.3 (live) "Photos" |  |  | 1 |  | Mark OLC2 inactive & Deleted assets as 'not live' | UAT | [5 empty] | Extra feature - determined after migration scripts run
416.2 | OLC 3.0.4 (beta) "Photos in After-Sales" | OLC UI | WAM data migration | 2 |  | As an after-sales user, I expect that relevant photo assets for the SKUs I have purchased will be visible to me shortly after they've been added to WAM | UAT |  | Low | High | 2007-04-18 | n | store asset message causes token check and file upload
522 | OLC 3.0.4 (beta) "Photos in After-Sales" |  |  | 2 |  | As an after sales user I want to be able to see thumbnails of the photos on the after sales screens | UAT
527 | OLC 3.0.4 (beta) "Photos in After-Sales" |  |  | 2 |  | As an OLC2 user logging into OLC3's after sales area, I expect to see photo assets for any programmes I have after-sales on. | UAT | [5 empty] | spray photos from WAM for all existing users
90.8 | OLC 3.0.4 (beta) "Photos in After-Sales" | OLC After-Sales UI | After-Sales | 1 | 5.1 to 5.4 | As an after-sales user, I want to be able to preview a photo before I download it. | Development
778 | OLC 3.0.4 (beta) "Photos in After-Sales" |  |  | 5 |  | As a user of WAM I expect everything related to Asets to work as it is meant to | UAT
779 | OLC 3.0.4 (beta) "Photos in After-Sales" |  |  | 2 |  | As a WAM users I don't expect to have any bugs in the system | Development
391.6 | OLC 3.0.5 (beta) "Discus in After-Sales" |  |  | 5 |  | When a new asset is added to Discus, it should be visible on the after-sales area of any user who has permissions on the right SKU | UAT | [5 empty] | discus service is live. Store assets message causes token check and file upload
415 | OLC 3.0.5 (beta) "Discus in After-Sales" | OLC UI | Discus data migration | 1 |  | When a user is given after-sales access to a particular SKU, all relevant Discus assets should be made availlable to that user via the OLC | UAT |  | Low | High | 2007-04-18 | n | Re-estimated as 1 point instead of 5. Some work completed as part of another story
526 | OLC 3.0.5 (beta) "Discus in After-Sales" |  |  | 3 |  | As an OLC2 user in after-sales, I expect to see discus assets for any programmes I have after-sales on | UAT | [5 empty] | spray discus assets for all existing users
786 | OLC 3.0.5 (beta) "Discus in After-Sales" |  |  | 1 |  | As a Discus user, when I delete an asset I expect it to be removed fomr the OLC | UAT
122 | OLC 3.0.6 (live) "Fine tuning" | OLC UI | Admin | 2 | 18.1 | As a staff user of the OLC with appropriate security permissions browsing the OLC from the intranet, I want to see a link on every page that takes me to the admin site so that I don't have to keep two windows open on my desktop at once Use BBC IP address range to decide whether to hide / show the link | UAT | Medium NA | Medium | Low | 2007-04-25 | n
243 | OLC 3.0.6 (live) "Fine tuning" | OLC UI |  | 3 |  | As an existing OLC2 user logging onto OLC3 for the first time, I should be sent to a special page to accept some legal Ts&Cs before I can access the site. | Development
298 | OLC 3.0.7 (live) "Go-Live" |  |  | 1 |  | Setup email addresses for regional emails to be received into (Kerry's email of 13 December) | To do
523 | OLC 3.0.7 (live) "Go-Live" |  |  | 5 |  | catch-up migration of users & assets that were granted since 3.0.1 | To do
524 | OLC 3.0.7 (live) "Go-Live" |  |  | 1 |  | As a wam user clicking an show on OLC link from WAM I want to be taken to the www.olc site | To do
525 | OLC 3.0.7 (live) "Go-Live" |  |  | 1 |  | As a user typing www.bbcworldwidetv.com I expect to see OLC3 | To do
529 | OLC 3.0.7 (live) "Go-Live" |  |  | 1 |  | Provide a friendly error page in OLC | Systest
530 | OLC 3.0.7 (live) "Go-Live" |  |  |  |  | Ensure MIP website is stored on a server that the OLC3 front page "Trade markets" can access. No work for the OLC3 team. Should be done by whoever hosts the MIP tv site
164
|  |  | Phase 2 below | [10 empty] | 117
ID | PHASE II FEATURES BELOW | Surface Point | Theme | Pts | Satisfaction Criteria | Feature | Phase 2 business priority | Analysis required | Business Risk | Tech Risk | Last Reviewed | Plumbing Involved? & FP | Plumbing FP | CAPEX
Do if we have time
528 |  |  |  | 2 |  | Clean up weblinks in WAM Live so we don't link to broken links
519 |  |  |  | 3 |  | make Favourites search link work on home page left hand menu, if required from UAT
699.2 | [5 empty] | As a user I want to see the various types of contributor names in ORAC appear on the OLC Programme Page under the appropriate headings, as soon as they are changed in ORAC. i.e. do live updates via messaging
346 | M | OLC UI |  | 5 |  | As a user, I want to be able to hit the back button in the browser and have the site behave as I would expect, (for instance just redrawing the previous screen) |  | SA |  |  | 2007-04-25 | n
37.1 | L | OLC UI | Indie Logo | 5 | 11.8 | Programme Page will display the Indie logo of the Independent Production company, where applicable if no logo exists, should just display nothing |  | SA | Low | Low | 2007-04-13 | n
695 | M | WAM UI | Programme copy | 3 |  | As a user entering or amending the contents of the programme copy tab I want an email to be sent to a general "Sue Cowley" email address "WW Product Development" to show all fields on the Programme Copy tab and the Marketing section (title, genre, duration etc.). The email should say "The following product has had new/amended data in WAM which you may wish to put into ORAC."
134 | M | OLC UI | Homepage Rollover | 3 | 10.1 | When rolling over any of the main boxed links on the homepage, extra headline information, specified in the CMS should be displayed |  | NA |  |  |  | n
133 | M | OLC UI | Homepage Rollover | 3 | 10.1 | As a logged in user who rolls over any of the placeholder boxes on the homepage, I want the box to expand, fish-eye style |  | NA |  |  |  | n
15 | M | OLC UI | Search | 3 | 1.6 | User sees the results grouped by TV Programme / Format Only into two separate result tables (maybe tabbed etc) |  | BA |  |  |  | n
27
Not to be done in Phase 1
659 | L | WAM UI | Festivals | 2 | WAM 7.7 | As an administrator I want to be able to maintain the list of festivals
704 | L | WAM UI | Festivals | 1 | WAM 4.9 | As a user who can edit an Activity, I want to be able to set or change the festival, including via the Marketing Plan
758 | L | WAM UI | Photos | 5 |  | Change the way photos are linked to the MCI data so that, if the database IDs are lost, we can recover the assets.
325.4 | L | OLC UI | Preview | 5 | 11.7 | As a client who has no high/low resolution preview preference, I want the system to attempt to automatically detect my connection bandwidth and set it for me, recording the setting in My Profile |  | NA |  |  |  | n
479 | L |  |  | 13 |  | Performance test and tune the OLC3 website and admin site |  | NA | NA |  | 2007-06-19
470 | L |  | Security | 5 |  | Secure the OLC web service |  | NA | NA
531 |  |  |  | 2 |  | As a user I want to re-enter my current password before changing it so that somebody else cannot change it for a joke
532 |  |  |  | 1 |  | AAPS should only send one error message email per badly formed preview filename so that we notice new files with bad names
533 |  |  |  | 2 |  | If OLC3 needs to be deployed or breeaks, assets should continue to be copied as normal
534 | [5 empty] | AS an OLC3 user I would like the sub genre on advanced serach page to load without reloading the page so that I cannot search without the genre when I think I have selected one
241 | OLC 3.0.0 (beta) "Search" |  | Durable subscribers | 3 |  | Durable subscribers: If a messaging listener goes off line for any reason, messages should not be lost, and should be replayed when it comes back on line | Systest
781 |  |  |  | 3 |  | WAM should check AAS at the end of each day making sure all it's live assets are on the CDN and all it's live assets have been withdrawn from the CDN
42
| High 1st |  |  | High 1st
45 | High 1st | OLC UI | Brand related search | 3 | 11.5 | Brand Related Material link will allow user to browse to related programmes within the OLC | High 1st |  |  |  | 2007-04-24 | n
37.2 | High 1st | WAM CMS UI | Indie Logo | 20 | 11.8 for ui, no use case for storage etc. | As a content admin I want to be able to store Indie logos so that OLC can display them on the website | High 1st |  | Low | Low | 2007-04-13 | n ? | 3
502 |  | OLC After-Sales UI | Preview requests |  |  | Suppose there are 2 MCIs that both show the same episode. If I ask for previews to MCI 1, I expect that "my previews" will show "MCI 1" and not a random selection from "MCI 1" and "MCI 2"
37.3 | High 1st | OLC UI | Programme Page | 8 | 11.x | As a user, when I click on an Indie logo on the programme page, I want to see a search results page for all programme which were made by that Indie | High 1st |  |  |  |  | n
489 | High 1st | OLC UI | Help/FAQ | 1 |  | As a user I want to be able to access an FAQ screen (assumes this is a just a single list of FAQs) | High 1st |  |  |  | 2007-07-24
214 | High 1st | OLC UI | Preview | 3 |  | As a view direct user, when I already have access to previews from an MCI, I want other newly encoded episodes to be available on the Programme Page Preview Tab automatically as soon as they are on the CDN. No emails would be sent to confirm this has happened. The related email templates delivered in Phase 1 would need to be amended to explain that this now happens. | High 1st |  |  |  | 2007-07-24
375.1 | High Dec 07 | OLC UI | Contributors | 8 | 11.9 | As a user I want to be able to select a cast member name from the programme page info tab and see search results of all of the MCIs (or ORAC products?) that include their name. | High Nov 07 |  |  |  |  | n
375.2 | High Dec 07 | WAM UI | Contributors | 13 |  | As a user I want to set up the contributor data in WAM, based on the data coming from ORAC. | High Nov 07
|  |  |  | 3 |  | extra points available to be used with 3-developer team working for 9 weeks up to 28/3/08
| High 1st |  |  | 59
| High |  |  | High
138 | High 1st | OLC UI | Search | 13 | 1.4 | As a user doing an advanced search, I want to be able to refine the result by specifying Available on Preview (note showing just this data in search results page would be 5 points) | High 1st |  |  |  |  | n
424 | High Nov 07 | OLC UI | Favourites | 5 | 10.3 | As a user I want to see an advanced favourites button which displays a search results screen | High Nov 07 |  |  |  | 2007-04-24 | n
52 | High Nov 07 | OLC UI | Preview Player | 3 | 11.7 | As a logged in user viewing preview content, I want to be able to make notes about the MarketingCatalogueItem while watching the preview | High Nov 07 |  | Medium | Low | 2007-04-13 | n
55 | High Nov 07 | OLC UI | Preview Player | 1 | 11.7 | As a logged in user viewing preview content, I want a link / button that allows me to email the notes to myself | High Nov 07 |  | Medium | Low | 2007-04-13 | n
51 | High | OLC UI | Preview Player | 2 |  | As a logged in user viewing preview content, I want to see time of the current frame through the whole clip | High |  |  |  |  | n
690 | M | WAM UI - Admin | Re-allocate | 1 |  | As an admin, I cannot deactivate a user unless their responsibilities have all been re-allocated
664.2.1 | M | WAM UI - Admin | Re-allocate | 2 |  | As an admin, I want to be able to be able to replace the person in a single-member role so that the reminders associated with that role are re-allocated to the new person
664.2.2 | M | WAM UI - Admin | Re-allocate | 5 |  | As an admin, I want to be able to view a particular user's current responsibilities to MCIs, Activities or Tasks, and re-allocate then (and thus any associated reminders) to another user.
483 | High |  | SPS | 20 |  | Automatic Update of SPS accessories based on assets being stored in WAM/Discus | High |  |  |  | 2007-07-24
484 | High |  | SPS | 20 |  | Integration of SPS to OLC - i.e. when an accessory order is placed it interfaces with Discus/WAM and provides users with access directly (no manual intervention) | High |  |  |  | 2007-07-24
485 | High | OLC UI | Regional pages |  |  | Regional/Foreign language version home pages (NEEDS FURTHER ANALYSIS) | High
486 | High Dec 07 | WAM UI | Contributors | 3 |  | Adding non-BBC programme credits to contributors | High Nov 07 |  |  |  | 2007-07-24
46 | High | OLC UI | Global Marketing | 20 | 11.6 | when viewing a programme page, I want to be able to see grouped PDFs against that MarketingCatalogueItem, grouped by Sales Region, uploaded by Creative Services that show how the programme has been marketed in other countries, and how successful that was i.e. the Programme page: Global Marketing tab | High |  |  |  |  | n
370 | High | OLC UI | Global Marketing | 1 | 11.3 | As a user I only want to see the Global marketing tab if there is global marketing material available for that MCI | High |  |  |  |  | n
62.1 | High | OLC UI | Breadcrumbs | 2 | 20.1 | As a logged in user I want to see a simple breadcrumb on each screen based on the screen hierarchy and access to the home page from every screen | High |  |  |  | 2007-04-25 | n
62.2 | High | OLC UI | Breadcrumbs | 5 | 20.1 | As a logged in user viewing any page on the site, I want to see sophisticated bread crumbing links at the top the page so that I know where I am in the navigation hierarchy and can easily navigate back up | High |  |  |  | 2007-04-25 | n
427 | High | OLC UI | Breadcrumbs | 1 |  | As a user, I want to be able to hit the Refresh button in the browser and have the site behave as I would expect | High |  |  |  | 2007-04-24 | n
445 | High | OLC UI | Announcements | 5 |  | As a user I want to see announcements of improvements to the site when I next visit (includes announcements CMS page) | High |  |  |  | 2007-07-24
487 | High | OLC UI | Strand | 3 |  | As a user I want to see strand URLs automatically added to the programme pages (includes CMS strand list page) | High |  |  |  | 2007-07-24
| High |  |  | 112
| reports (high?) |  |  | reports
495 | reports | Reports |  | 5 |  | As a users I want to see a list of users who have never visited OLC3 | reports (high?) |  |  |  | 2007-07-24
384.1 | reports | INFOcentre reports | INFOcentre reports | 20 | separate spec | INFOCENTRE team's work to deliver reports. Planned originally to be 20 working days | reports (high?)
384.2 | reports | INFOcentre reports | INFOcentre reports | 8 |  | as the system I want to collect the information needed for the iNFOcentre reports - 2 tasks: understand and implement | reports (high?) |  |  |  |  | y | ?
496 | reports | INFOcentre reports | After Sales reports | 8 |  | As a user I want to be able to export the admin after sales data, but I want to consider this as part of reviewing the Info Centre reports | reports (high?) |  |  |  | 2007-07-24
497 | reports | INFOcentre reports | Previews reports | 8 |  | As a user I want to be able to export the admin preview data, but I want to consider this as part of reviewing the Info Centre reports | reports (high?) |  |  |  | 2007-07-24
| reports (high?) |  |  | 49
| Med Jan 08 |  |  | Med Jan 08
64 | Med Jan 08 | WAM CMS UI | OLC3 banner | 3 | 6.7 and 10.1 | As an OLC Content Admin, I want to be able to replace the animated banner that appears at the top of all OLC pages using the WAM UI. I want it to appear immediately on the home page | Med Jan 08 |  |  |  |  | n
83.1 | Med Jan 08 | WAM CMS UI | News Items | 5 | 6.3 | As a content Administrator, I want to be able to create News Items that relate to a MCI | Med Jan 08 |  |  |  |  | n
83.2 | Med Jan 08 | WAM CMS UI | News Items | 8 | 6.11 | As a content Administrator, I want to be able to create News Items that don't relate to a particular MCI, and will have up to three assets associated with them | Med Jan 08 |  |  |  |  | n
83.3 | Med Jan 08 | WAM CMS UI | News Items | 3 | 6.1 | As a content administrator, I want to be able to review and amend the news items that will appear for a particular marketing genre. | Med Jan 08 |  |  |  |  | n
83.4 | Med Jan 08 | WAM CMS UI | News Items | 2 | 6.1 | As a content administrator, I want to be able to review and amend the news items that will appear on the news & ratings page | Med Jan 08 |  |  |  |  | n
109.3 | Med Jan 08 | WAM CMS UI | Genre Banner | 5 | 12.1 | As content admin, I want to be able to associate a flash banner with each Marketing Genre to be displayed on the Genre Homepage | Med Jan 08 |  |  |  |  | n
109.4 | Med Jan 08 | WAM CMS UI | Genre Banner | 3 | 12.1 | As content admin, I want to be able to associate a flash banner with the news & ratings 'genre' to be displayed on news & ratings page | Med Jan 08 |  |  |  |  | n
110.2 | Med Jan 08 | WAM CMS UI | Themed Promotions | 5 | 6.4 and 6.5 | As content admin, I want to be able to create / edit / delete a list of Themed Promotions, each of which has an associated PDF document (replacing the developers' Time New Roman screen) | Med Jan 08 |  |  |  |  | n
112 | Med Jan 08 | WAM CMS UI | Featured Programme | 8 | 6.10 | As content admin, I want to be able to associate an image or other media to be displayed in the Featured Programme box on the homepage | Med Jan 08 |  |  |  |  | n
150 | Med Jan 08 | WAM CMS UI | Content Management | 3 | 6.9 | As a content admin, I want to upload the PDF documents that will be displayed on the Quarterly Highlights page and the Digital media page of OLC | Med Jan 08 |  |  |  |  | n
314 | Med Jan 08 | WAM CMS UI | Content Management | 13 |  | If a new Asset is added via WAM to the DMS that is part of the core OLC content (e.g. Genre banner) it should be immediately uploaded to the CDN so that OLC3 can render it. | Med Jan 08 |  |  |  |  | n
380 | Med Jan 08 | WAM CMS UI | Content management | 3 | 6.8 | As an authorised user I want to see a CMS home page so that I can navigate to the other CMS pages | Med Jan 08 |  |  |  |  | n
381.1 | Med Jan 08 | WAM CMS UI | Print Catalogue | 5 | 6.6 | As content admin, I want to be able to associate up to 5 print catalogues for display in the OLC Home Page | Med Jan 08 |  |  |  |  | n
382 | Med Jan 08 | WAM CMS UI | Homepage Rollover | 5 | 6.7 | As content admin, I want to be able to associate pictures and rollover text for the fixed set of OLC Home Page icons | Med Jan 08 |  |  |  |  | n
386 | Med Jan 08 | WAM CMS UI | Marketing Kit | 5 | WAM | As an content admin, I want to be able to change the list of asset types that zip up into the Marketing Kit from the WAM UI. | Med Jan 08 |  |  |  |  | n
494 | Med Jan 08 | WAM CMS UI | Home page | 20 |  | As a content admin, I want to be able to manage the 6 home page icons and their interactions flexibly, so I can choose from a range of interactions as well as an icon and rollover wording | Med Jan 08 |  |  |  | 2007-07-24
| Med Jan 08 |  |  | 96
| Med Feb 08 |  |  | Med Feb 08
43 | Med Feb 08 | OLC UI | Marketing Kit | 5 | 11.5 | As a user viewing the Marketing Materials tab on the programme page, I want a Marketing Kit link which allows me to download a zip file containing a group of assets related to that MCI, from a fixed list of asset types. | Med Feb 08 |  |  |  |  | n
462 | Med Feb 08 | Admin UI | After Sales Maintenance | 2 | 7.3 | As an after-sales admin I wish to search for users that have after-sales and show 'Current After Sales' totals | Med Feb 08 | NA
463 | Med Feb 08 | Admin UI | After Sales Maintenance | 2 | 7.3 | As an after-sales admin, after I have selected a user and selected a programme, I wish to view an 'Current after sales' tab. The Current After-Sales tab should show the 'Date Granted' and 'Last Accessed' dates against each programme | Med Feb 08 | NA
464 | Med Feb 08 | Admin UI | After Sales Maintenance | 2 | 7.3 | As an after-sales admin, after I have searched for programmes, I wish to see the 'Current Access' totals against each programme, and current totals of each asset type | Med Feb 08 | NA
465 | Med Feb 08 | Admin UI | After Sales Maintenance | 2 | 7.3 | As an after-sales admin, I wish to search for and select a programme and view users with After-Sales access | Med Feb 08 | NA
466 | Med Feb 08 | Admin UI | After Sales Maintenance | 2 | 7.3 | As an after-sales admin, I wish to search for and select a programme and view users with 'Current After Sales' information. Information displayed will be Title, Company, Email, Date Granted | Med Feb 08 | NA
457 | Med Feb 08 | Admin UI | After Sales Maintenance | 1 | 7.32 | As an after-sales admin I wish to search for users that have after-sales and show an 'Expired After Sales' total (previously deferred functionality) | Med Feb 08
458 | Med Feb 08 | Admin UI | After Sales Maintenance | 1 | 7.32 | As an after-sales admin, after I have selected a user and selected a programme, I wish to view an 'Expired after sales' tab. The Current After-Sales tab should also show the 'Access Expires' date against each programme, and also allow programmes to be selected and access removed for that user (previously deferred functionality) | Med Feb 08
459 | Med Feb 08 | Admin UI | After Sales Maintenance | 1 | 7.32 | As an after-sales admin, after I have searched for programmes, I wish to see the 'Expired Access' total against each programme (previously deferred functionality) | Med Feb 08
460 | Med Feb 08 | Admin UI | After Sales Maintenance | 1 | 7.32 | As an after-sales admin, I wish to search for and select a programme and view users with after-sales access; the information displayed should include the Date of expiry (previously deferred functionality) | Med Feb 08
461 | Med Feb 08 | Admin UI | After Sales Maintenance | 1 | 7.32 | As an after-sales admin, I wish to search for and select a programme and view users with 'Expired After Sales' information (previously deferred functionality) | Med Feb 08
449 |  | Admin UI | After-Sales Admin | 3 | 7.27 | As after-sales admin, I want to be able to search for users that have after-sales and show 'Current After Sales' totals and then I want to be able to send them a script notification email to say that new scripts have been made available. User should get an email. The link in the email should make OLC3 default to the Scripts selection within the after-sales assets area |  | NA |  |  | 2007-06-12
90.7 | Med Feb 08 | OLC After-Sales UI | After Sales | 13 | 5.1 to 5.4 | As a client of BBCWW who has selected some of their after-sales assets for download but is worried that the download might fail, I want the site to ensure that all the files are downloaded to my computer it resets my selections | Med Feb 08 |  | Medium | Medium | 2007-04-13 | n
450 | Med Feb 08 | Admin UI | Preview Admin | 13 | 7.25 | As a sales person, I want to be able to search for a client to identify the preview clips they have permissions on and search for preview clips to see who has access. I also want to be able to remove user's access to them. | Med Feb 08 | NA
426 | Med Feb 08 | Admin UI | Preview Admin |  |  | As an sales administrator, and OLC admin user I want to be able to see a list of all Preview and DVD requests (NEEDS FURTHER ANALYSIS) | [5 empty] | n
| Med Feb 08 |  |  | 49
| Low |  |  | Low
490 | Low | OLC UI | Themed Promotions | 20 |  | As a user I want to see on a programme page whether that programme is part of a current themed promotion, includes WAM work to attach themed promotion info to MCIs | Low |  |  |  | 2007-07-24
435 | Low | OLC UI | Preview | 5 |  | As a staff user I want to view all preview content from OLC, rather than just from OLC admin | Low | SA |  |  | 2007-07-24 | y | 1
56 | Low | OLC UI | Preview Player | 1 | 11.7 | As a logged in client user viewing preview content, I want a link that allows me to create and send an Outlook email to my BBC WW Sales Team | Low |  |  |  | 2007-04-24 | n
83.7 | Low | CDN | Housekeep News items | 5 | 6.1 | If a non-MCI news item is disabled, any related assets should be removed from the CDN | Low |  |  |  |  | y | 1
307 | Low | CDN | Housekeep CDN Assets | 8 |  | An OLC background task needs to be able to request that items be removed from the CDN (and the archive consequently updated) if all client Permissions on a given Asset have expired, so that expensive CDN storage space is not wasted. | Low |  |  |  |  | y | 8
310 | Low | CDN | Housekeep After-Sales Assets | 8 | 5.5 | If a client's after-sales access permission to a SKU is removed, any Photo or Discus Assets relating to that SKU should be removed from the CDN if no other clients have permission to view them. | Low |  |  |  |  | y | 2
388 | Low | CDN | Housekeep Home page icons | 5 | 6.7 | When a homepage icon is changed, the old image should be removed from the CDN | Low |  |  |  |  | y | 1
428 | Low | CDN | Housekeep Inactive MCIs | 8 |  | As the system, when an MCI becomes inactive, I want all assets to be removed from the CDN, and all permissions revoked | Low |  |  |  | 2007-04-25 | y | 2
468 | Low | CDN | Housekeep CDN (Recovery) | 8 |  | As a systems support person, I want to be able to run a script to ensure that all assets that should be on the CDN are there. This would be used for instance in the event of a disk failure on the CDN. | Low |  |  |  | 2007-07-24
7 | Low | OLC UI | Save Search Query | 5 | 1.7 | From the advanced search page, user can save a search query for future re-use (dynamic) | Low |  |  |  |  | n
8 | Low | OLC UI | Save Search Query | 5 | 1.7 | User can review and re-use the list of saved search queries | Low |  |  |  |  | n
16 | Low | OLC UI | Save Search Results | 5 | 1.7 | From the search results page, user can save all or a subset of the MarketingCatalogueItems returned so that they can review them later, perhaps to show to a colleague | Low |  |  |  |  | n
17 | Low | OLC UI | Save Search Results | 5 | 1.7 | User can review the list of saved static searches | Low |  |  |  |  | n
86.2 | Low | OLC UI | Mini Catalogue | 2 | 2.13 | As a logged-in user, I want to be able to group a selection of MarketingCatalogueItems together as a Mini Catalogue and email them to someone (feature 86.1 was print them) | Low |  | High | Low | 2007-04-13 | n
88 | Low | OLC UI | Housekeep Inactive Users | 3 | 3.2 | As the system, If a user has attempted to register with the site and that registration is not activated within a sixty day period, that account should be deleted automatically. | Low |  | Low | Low | 2007-04-13 | n
491 | Low | OLC UI | Preview icon | 5 |  | As a user I want the "My Preview" icon to show a picture of my latest preview | Low |  |  |  | 2007-07-24
437 | Low | OLC UI | Favourites icon | 13 |  | As a user, I would like the "My favourites" icon to change in response to the genre of or the programme image of the latest favourite for that user. | Low |  |  |  | 2007-07-24 | n
492 | Low | OLC UI | Favourites and Previews icons | 13 |  | As a user I would like the Favourites and Previews icons to fan out as they do in Digi showcase, if performance can be made good enough and estimate assumes that the fanning is limited to 3 pictures) | Low |  |  |  | 2007-07-24
493 | Low | OLC UI | Linked programmes | 5 |  | As a user I want to see linked programmes as described in ORAC's related products (once ORAC has this data) | Low |  |  |  | 2007-07-24
| Low |  |  | 129
| TBC |  |  | TBC |  | Below are features which have not yet been prioritised
498 | TBC | Decommission bbcprograms.com |  |  |  | I want the bbcprograms.com website replaced (this site is aimed at US PBS buyers and provides marketing materials and programme synopses) (NEEDS FURTHER ANALYSIS) | TBC
86.1 |  | OLC UI | Mini Catalogue | 13 | 2.13 | As a logged-in user, I want to be able to group a selection of MarketingCatalogueItems together as a Mini Catalogue for printing |  | SA | High | Low | 2007-04-13 | n
53.2 |  | OLC UI | Preview Player | 2 | 11.7 | As a logged in user viewing preview content, I want an improved behaviour in that list of preview clips will be paginated |  | NA |  |  | 2007-04-24 | n
225 |  | Admin UI | Make CD | 5 | 7.33 | As a user I want to search for SKUs and their after sales assets and choose to download some or all of the assets for a SKU so I can make a CD to send off to a client who does not have online access to the OLC3 client after sales site
211 |  | ORAC | Marketing Genres | 5 |  | As an ORAC user I want to be able to flag marketing genres as active/inactive and for only the active ones be published for use in systems such as OLC. |  |  |  |  | 2007-07-17
221.2 | TBC | WAM | Marketing genres |  |  | As the WAM system I want to subscribe to a service provided by ORAC and update my local cache of Marketing Genres | TBC
221.3 | TBC | OLC UI | Marketing genres |  |  | As the OLC system I want to subscribe to a service provided by ORAC and update my local cache of Marketing Genres | TBC
222 | TBC | ORAC | Marketing genres |  |  | As a user of ORAC I want to be able to manage the marketing genres in the ways defined in the <marketing genres functional description v02.doc> | TBC
223 | TBC | WAM | Marketing genres |  |  | As a WAM user I want to receive a report when 1 or more MCIs do not have a PMG, and when 1 or more MCIs do not have an MG | TBC
25 | TBC | WAM | Marketing genres |  |  | As a WAM user, when an MCI does not have an MG (either because I have not selected one yet, or because a previous MG has been deleted in ORAC, then I want the MCI to be made inactive. | TBC
436 | TBC | OLC UI | Marketing genres |  | 1.8 | 8 points. As a user viewing the search page on the OLC, I expect the list of sub-genres and related marketing genres to be up-to-date, synchronised with the source system that they were originally stored in. | TBC | NA |  |  | 2007-04-25 | y | 5
482 | TBC | Decommission OLC2 | Preview service | 20 |  | Make the final version of the preview service, replacing our tactical approach with clean access to the DCS previews without relying on the OLC2 backend (Can only be done when OLC2 is no longer in use) | TBC |  |  |  |  | y | 20
442 | TBC | Decommission OLC2 |  | 20 |  | As a user I want assets held on OLC2, but not used in OLC3 Phase 1, to be migrated to WAM or similar so that I can still access them. | TBC |  |  |  | 2007-07-24
443 | TBC | OLC UI | Logon | 2 |  | As a user of the OLC who enters an incorrect password X times, I expect that my account will be disabled. I expect to get an email informing me of this. If I attempt to log in I should be informed that my account is disabled. (From bug 435) | TBC | SA |  |  |  | n
212 | TBC | OLC Admin | Logon | 3 |  | As an authorised administrator, I want to be able to see a list of locked users accounts and be able to unlock them. (From bug 435) | TBC | SA |  |  |  | n
213 | TBC | OLC UI | New to Preview | 2 |  | As a user viewing the New to Preview items from the Home Page link, I want to see a flag which tells me whether all episodes of that MCI have been encoded | TBC | SA |  |  | 2007-07-24
160 | TBC | OLC UI | New to Preview | 8 |  | As a user of OLC, I would expect all newly encoded content to appear on the CDN for 30 days after encoding, so that when I request access to view it, there is no delay in putting it up onto the CDN. | TBC | SA |  |  | 2007-07-24
53.3 | TBC | OLC UI | Preview |  |  | 3 points. As a user who has been granted preview permissions on a particular MCI and received an email with a link to that MCI, I would expect to see that same MCI in my recent previews drop-down, rather than any random MCI that shares the same episodes. Existing data in OLC3 when this is implemented may need to be amended to ensure the same consistency for all existing MCIs | TBC |  |  |  | 2007-07-04
438 | TBC | OLC UI | Preview Player | 3 |  | As a logged in user viewing preview content, I want an improved behaviour in that the "now playing message" should perhaps include the episode synopsis from ORAC where one exists, else show the MCI synopsis if it can fit in the space. | TBC |  |  |  | 2007-07-24
| TBC |  | Discus |  |  | There may be new requirements coming out of the Discus data work being done | [5 empty] | n | ?
635 | M | WAM UI - Activity | Activities | 1 | WAM | As a user viewing the activities tab for an MCI, I want to be able to create new activities from the existing templates in the system, adding back all of the "leakage" from the earlier simple views of activities
734 | M | WAM |  | 5 | WAM | Data cleansing tool for Creative Services to do contributor data etc.
735 | M | WAM |  | 3 | WAM | As a view only user on the Show Photo page I should only be given a thumbnail so that I cannot distribute files I don't have rights to.
736 | M | WAM |  | 2 | WAM | As a WAM users, when I click on save on Programme copy and Production details tabs I want to be able to see an error message when there are some errors. I do not want to have the error messages on a part of the page I cannot see in front of me
737 | M | WAM |  | 0 | WAM | Bug 2064. As a user searching for activities and tasks I should have to complete at least one search parameter
738 | M | WAM |  | 1 | WAM | As a developer I want to see a diagnostics page to show the health of the ORAC to WAM messaging link.
739.2 | L | WAM |  |  |  | As a user viewing an MCI photos tab I want the sort order to be by Version, then within each version, Generic first then Episodes in order, and within generic and episode, by photo name.
739.3 | L | WAM |  |  |  | As a user viewing Programme search results, I want the MCI titles to be in ascending alphabetical order within their product
739.4 | L | WAM |  |  |  | As a user viewing the Asset search tab and the MCI Activity tab I want all columns to be sortable
739.1 | 21 H | WAM |  | 5 |  | As a user viewing tabulated data, I want it to be sorted, by default, in a logical way. (see high priority card for more details)
618 | L | WAM UI | Tasks | 1 |  | As a user looking at my todo list I want to be able to click a task and navigate to a page where I can view the task so that I can edit it
649.2 | L | WAM UI | Tasks | 1 |  | As a user I want to be able to search for tasks including exporting results to an Excel spreadsheet
650 | L | WAM UI | Tasks | 5 |  | As a user I want to be able to create, amend and complete a task, uploading the asset if there is one associated with the task
658 | L | WAM UI | Tasks | 1 |  | Set up the default task types from section 4
720 | L | WAM UI | Tasks | 2 |  | As an admin, I want to be able to specify whether a custom asset type is an "Activity" or "Task" asset so that the appropriate list of asset types is offered when creating a new task or activity template
701.3 | L | WAM UI - Todo List | Tasks | 1 |  | As a user clicking on a reminder, I expect to be taken to the 'view task' page if it's about a task.
615 | L | WAM UI | Tasks | 2 |  | As a user with a todo list I want to be able to see all my outstanding tasks, colour coded correctly
711 | L | WAM UI | Tasks | 3 |  | As an administrator I expect users to see reminders associated with a reminder template with a date type of 'linked task template due date rule'
721 | L | WAM UI | Tasks | 3 |  | As a user I want to be able to store and retrieve non-MCI-related assets, i.e. any AssetType marked 'Task' (see #720)
717 | L | WAM UI - Admin | Activity Templates | 5 |  | As a user I would like to be able to create and edit activity templates
732 | [5 empty] | Fix bugs found in UAT 2
709.3 | L | WAM UI - Admin | Activity Templates | 1 |  | As an admin, I expect the system to stop me from changing the Asset Type for locked down templates
745 | L | WAM |  | 2 |  | As a user if I check all episodes of a single-SKU MCI and press save, then it should become and be validated as a whole product MCI.
746 |  | WAM |  | 3 |  | As a photo user I want the photo notes field on the production details to allow me to insert limitless text with each entry to have user name and date.
747 |  | WAM |  | 1 |  | Show TX Season and Tx Year and Tx channel as new columns in the existing SKU table (see bug 2046)
748 |  | WAM |  | 3 |  | As an admin, when I change a reminder template prompt rule, I want the right effect on existing reminders - discuss with Kerry first the approach to recalculation and the effect on todo lists.
749 |  | WAM |  | 2 |  | As a users I want to be able to search for assets by festival
750 |  | WAM |  | 3 |  | As a user I would like the effect of pressing the cancel button to be as if I had pressed the Back button so that the previous page does not have to reload and slow me down
751 |  | WAM |  | 2 |  | As a user I would like to see the Programme Image, if there is one, on the various MCI tabs, as shown in the MCI prototype
752 |  | WAM |  | 3 |  | As an admin, when I change an activity template prompt rule, I want the right effect on existing activities - discuss with Kerry first the approach to recalculation and the effect on todo lists.
753 |  | WAM |  | 1 |  | As a user I want the system to ensure that each Asset type can only be related to one activity template (needs an appropriate error message in the activity template edit screen)
755 |  | WAM |  | 1 |  | Update reminder templates so a user can choose which task I want my reminder template to be linked to.
756 |  | WAM | Product Panel |  |  | As a user I want to see an HD flag displayed on the Product panel of WAM, using the same approach as is already used in OLC3
757 |  | WAM |  |  |  | As a user I want to see whether the product is a TV or Format (medium code = 1 or 2) on the Product panel on WAM
758 |  | WAM and ORAC |  |  |  | As a user I want to see that products are Motion Gallery, rather than ordinary Tv or Format. Details still to be defined.
759.1 |  | WAM and OLC3 | Press kit asset |  |  | As a user I want the newly created press kit assets from WAM to be made into a core asset and included in the OLC3 group of assets called Marketing Kit so that they are downloaded with the other similar assets from the link on the OLC3 Programme Tab
758.2 |  | WAM and OLC3 | Press kit asset |  |  | As a user I want selected OLC2 assets to be migrated into WAM as Press kit assets, under rules yet to be determined by Kerry Travers. E.g. the required assets may not all be neatly name d "press kit" in OLC2
760 |  | WAM and OLC3 | Artwork |  |  | As a user I want to be able to upload multiple artwork assets in WAM, with a title for each, and for all of them to be downloadable as after sales items
761 |  | WAM and OLC3 | Square Eyes |  |  | As a user I want to be able to upload multiple Square Eyes assets in WAM, with a title for each, and for all of them to be downloadable as after sales items
762 |  | WAM | programme search |  |  | As a user I want the strand to be included in the WAM programme search results
763 |  | WAM and OLC3 | Text formatting |  |  | As a user I want the various programme copy fields to be able to have bold, italics, and underline and for these to be shown on OLC3
764 |  | WAM | General tab |  |  | As a user I want to see the ORAC rights field on the WAM MCI general tab
765 |  | WAM | Asset deletion |  |  | As a user I want to be able to delete assets from WAM
766 |  | WAM | MCI deletion |  |  | As a user I want to be able to delete MCIs from WAM
767 |  | WAM | Reminders |  |  | a new reminder called Final Ratings (Prompt date - 21 days after last episode TX date / Due date - 28 days after last episode TX date) (Cannot be added to WAM live in December 2007 as last episode Tx date is not available to the WAM reminders "template")
768 |  | All systems |  |  |  | As a user I want to know that changes to marketing titles are handled in a robust way and that they are rolled back if any part of the various system interfaces fails part way during the change. As an example: Changing an MCI title would cause assets to be amended, reminders to be amended, messages to go out to other systems like OLC. An unexpected failure part way through this process would leave things out of sync
769 |  | WAM | Promos |  |  | Promos - analysis / work required to establish whether a single 'version' of a promo can be saved in WAM that is in a suitable quality / encoding for other applications (i.e. digi app)
770 |  | OLC3 | Admin - staff |  |  | Can A.D be used to de-activate staff users from OLC3 access
782 | [5 empty] | As an OLC Admin In-house preview user, I expect to be able to filetr out programmes that have no previews without the screen being taken up with programmes that have no preveiws
787 | [5 empty] | As a developer maintaining the OLC suite of sites and services I want to be provided with more intelligent information about the services that are supposed to be listening and responding to each other so that if a service stops behaving as expected I will be able to respond appropriately
791 | [5 empty] | Ensure systems are able to cope with bug messages e.g. Eastenders | [6 empty] | Added to IT list 15/04/08
792 | [5 empty] | As an After Sales user bulk downloading assets. If an asset in my basket has been removed from the CDN after I have added it, it should be removed from my basket and I should be notified. | [6 empty] | Added to Biz list 15/04/08
| TBC |  |  | 146
Next Feature:795 |  |  | Phase 2 backlog | 640 | [8 empty] | 43
Don’t go over 599 : WAM is using 600 on
|  | VELOCITY | Contingency
|  | 0.9 | 95% | 46 | wks per year | At 0.9 FP per developer day, elapsed time to complete 640 feature points. Starting on 28/1/2008 | Cost per week | Costs
Summary | Dev team | (Developers - lead dev) * velocity | Developer days per week | Weeks worked | Elapsed years | 2008-01-28
| 2 | 1.539 | 7.695 | 83.1709 | 2.0167 | 2010-02-02 02:10 | 6825 | 715721.6713
| 4 | 2.9925 | 14.9625 | 42.7736 | 1.0372 | 2009-02-09 13:27 | 12425 | 670104.2461
Smaller team with 5% contingency | [5 empty] | By priority groups - although apportioning holidays evenly throughout the year
High 1st | 2 | 1.539 | 7.695 | 7.6673 | 0.18591 | 2008-04-19 20:36
High | 2 | 1.539 | 7.695 | 14.5549 | 0.35292 | 2008-08-26 16:11
reports (high?) | 2 | 1.539 | 7.695 | 6.3678 | 0.1544 | 2008-10-22 00:45
Med Jan 08 | 2 | 1.539 | 7.695 | 12.4756 | 0.3025 | 2009-02-09 10:40
Med Feb 08 | 2 | 1.539 | 7.695 | 6.3678 | 0.1544 | 2009-04-06 19:14
Low | 2 | 1.539 | 7.695 | 16.7641 | 0.40649 | 2009-09-02 04:04
TBC | 2 | 1.539 | 7.695 | 18.9734 | 0.46006 | 2010-02-17 02:10
weeks left after 31 March 2008 |  |  |  | 98.2986 |  | 2008-03-31
Larger team with 5% contingency
High 1st | 4 | 2.9925 | 14.9625 | 3.9432 | 0.095612 | 2008-03-17 21:34
High | 4 | 2.9925 | 14.9625 | 7.4854 | 0.1815 | 2008-05-23 03:31
reports (high?) | 4 | 2.9925 | 14.9625 | 3.2749 | 0.079407 | 2008-06-21 03:08
Med Jan 08 | 4 | 2.9925 | 14.9625 | 6.416 | 0.15557 | 2008-08-16 21:57
Med Feb 08 | 4 | 2.9925 | 14.9625 | 3.2749 | 0.079407 | 2008-09-14 21:33
Low | 4 | 2.9925 | 14.9625 | 8.6216 | 0.20905 | 2008-11-30 04:50
TBC | 4 | 2.9925 | 14.9625 | 9.7577 | 0.2366 | 2009-02-24 13:27
weeks left after 31 March 2008 |  |  |  | 47.223 |  | 2008-03-31
Larger team to finish by 31 March with 5% contingency
High 1st | 6 | 4.5315 | 22.6575 | 2.604 | 0.06314 | 2008-03-06 01:07
High | 6 | 4.5315 | 22.6575 | 4.9432 | 0.11986 | 2008-04-18 19:05
reports (high?) | 6 | 4.5315 | 22.6575 | 2.1626 | 0.052439 | 2008-05-07 22:26
Med Jan 08 | 6 | 4.5315 | 22.6575 | 4.237 | 0.10274 | 2008-06-14 10:25
Med Feb 08 | 6 | 4.5315 | 22.6575 | 2.1626 | 0.052439 | 2008-07-03 13:47
Low | 6 | 4.5315 | 22.6575 | 5.6935 | 0.13805 | 2008-08-22 23:07
TBC | 6 | 4.5315 | 22.6575 | 6.4438 | 0.15625 | 2008-10-18 23:50
weeks left after 31 March 2008 |  |  |  | 28.8561 |  | 2008-03-31
3-developer team with 5% contingency
High 1st | 3 | 2.3085 | 11.5425 | 5.1115 | 0.12394 | 2008-03-28 05:44
High | 3 | 2.3085 | 11.5425 | 9.7033 | 0.23528 | 2008-06-22 02:47
reports (high?) | 3 | 2.3085 | 11.5425 | 4.2452 | 0.10293 | 2008-07-29 16:30
Med Jan 08 | 3 | 2.3085 | 11.5425 | 8.3171 | 0.20167 | 2008-10-11 07:07
Med Feb 08 | 3 | 2.3085 | 11.5425 | 4.2452 | 0.10293 | 2008-11-17 20:49
Low | 3 | 2.3085 | 11.5425 | 11.1761 | 0.27099 | 2009-02-24 18:43
TBC | 3 | 2.3085 | 11.5425 | 12.6489 | 0.3067 | 2009-06-16 17:27
weeks left after 31 March 2008 |  |  |  | 63.2467 |  | 2008-03-31
Formulas:
Feature = G615+[Satisfaction Criteria]*365
Feature = G615+[Satisfaction Criteria]*365+15
Note on E12: Matt Wynne: we'll use Ajax to call a page on our server which fetches the news content, and auto-updates the news
Note on E13: Matt Wynne: includes build of the target page as well
Note on G28: - build lucine.net indexer - integrate indexer with task scheduler - build search subsystem - build search form in asp.net
Note on E39: Matt Wynne: Archive Subsystem Archive WebService Archive Database Preview Data Migration
Note on E40: Matt Wynne: assuming #18 is complete
Note on E82: Matt Wynne: where does this info come from? Where do we find the logo?

## Features (WAM)
ID | Iteration | Surface Point | Theme | Pts | Feature | Satisfaction Criteria |  | Business Risk | Tech Risk | Reviewed | % built in V1.0 |  | Phase
411 | 7 | WAM UI | Production Details | 5 | Allow users to create production details for the programme | 3.1
412 | 7 | WAM UI | Co-producer Dates | 5 | Allow users to create co-producer dates for production details | 3.2
413 | 7 | WAM UI | Filming Dates | 2 | Allow users to create filming dates for production details | requirement gone
415 | 7 | WAM UI | Custom Assets | 3 | Allow users to maintain the list of custom asset types | 7.1
|  |  |  | 15 | in 9 days
653 | 8 | WAM UI | Assets | 2 | As a user I want to be able to create new asset types or update existing ones | 7.5 | [5 empty] | WAM
657 | 8 | WAM UI | Tasks and Assets | 3 | As an administrator I want to be able to maintain task types and their associated assets | 7.6 (NEW) |  |  |  | Pete 26 hours 3/5/07 |  | CCI
633.1 | 8 | WAM UI | Marketing plan activities | 3 | Initial development of: As a user I want to be able to select the activities that need to be completed for the programme, from the list of default marketing activities defined in administration. (This function will only be invoked once per a programme.) Activity Data and Skelta Workflows will be created at this time | 3.4 and 4.2 and 4.4 | [5 empty] | WAM
|  |  |  | 8 | in 7 days
652 | 9 | WAM UI | Search | 2 | As a user I want to be able to search for ORAC products and see if there are MCIs so I can move to the MCI or create a new one | 8.6 (NEW) | [5 empty] | CCI
603 | 9 | WAM UI | Programme | 3 | As a user viewing an MCI I want to see the ORAC data on the General details tab | 1.2 (CCI) | [5 empty] | CCI
626 | 9 | WAM UI | Production details | 1 | As a user I want to be able to enter and amend the production details against a programme (note that filming dates is now a text field) | 3.1, 3.5 (was 3.1 and 3.2) |  |  |  |  | 85% | WAM
663 | 9 | WAM UI | Users | 1 | As an administrator I want to create/update users and assign them to roles | 7.4 |  |  |  |  | 100% | WAM
647 | 9 | WAM UI | Programme copy | 2 | As a users I want to be able to describe the programme, with programme copy information that must be completed before a programme can appear on OLC | 2.7 (CCI) |  |  |  | Pete hours 10/5/07 | 100% | CCI
9
678 | 10 | WAM UI | MCI activation | 1 | When an MCI is changed, the MCI details should be published to the bus for OLC to update its cache | 2.6 CCI | [5 empty] | CCI | 1
630 | 10 | WAM UI | MCI activation | 1 | As a user completing the Programme Copy tab I want WAM to make the MCI active if I have completed all of the mandatory fields. WAM will tick the "Active" checkbox | 3.1 (CCI) and 2.7 | [5 empty] | CCI | 1
679 | 10 | WAM UI | MCI activation | 5 | Manage MCI data from different updating screens on WAM | 3.1 and 2.7 | [5 empty] | CCI | 1
683.1 | 10 |  | refactoring | 5 | refactor UI sub system
673 | 10 |  |  | 2 | data migration of metadata from ORAC | 1.1 | [5 empty] | CCI
680 | 10 | WAM UI | All screens | 3 | Pagination of lists | various | [5 empty] | WAM | 1
17
682 | 11 |  | refactoring | 2 | Put WAM into cruise control |  |  |  |  | 2007-05-24
683.2 | 11 |  | refactoring | 7 | refactor UI sub system |  |  |  |  | 2007-05-24 | 100% | CCI
684 | 11 |  | refactoring | 2 | refactor application tier |  |  |  |  | 2007-05-24
602 | 11 | WAM UI | Programme | 3 | As the system I want to receive new or revised data from ORAC and store it | 1.1 and 1.4 (was 1.1, 1.2 & CCI) |  |  |  |  | 100% | CCI
14
629 | 12 | WAM UI | MCI contents | 5 | As a user I want to be able to add, amend and delete episode contents of the MCI in a separate window, and have the results displayed on the production details screen | 2.6 (CCI) |  |  |  |  | 100% | CCI | 1
682.2 | 12 |  | refactoring | 1 | Last part of Put WAM into cruise control
683.3 | 12 |  | refactoring | 1 | Last part of re-factor UI sub system
686.1 | 12 |  | refactoring | 5 | first part of refactor DMS sub system |  |  |  |  | 2007-05-24
688.1 | 12 |  | refactoring | 3 | first part of refactor security sub system |  |  |  |  | 2007-05-24
654 | 12 | WAM UI | Assets | 1 | Set up the default asset types from section 4 | section 4 | [5 empty] | WAM
627 | 12 | WAM UI | Co-producer details | 3 | As a user I want to be able to add, amend and delete co-producer details in a separate window, and have the results displayed on the production details screen | 3.2 was 3.3 |  |  |  |  | ?% | WAM
628 | 12 | WAM UI | Contacts | 2 | As a user I want to be able to add, amend and delete contacts in a separate window, and have the results displayed on the production details screen | 3.3 was a small part of 3.1 |  |  |  |  | 85% | WAM
21
668 | 13 | WAM UI | Assets | 3 | As a user I want to ensure that more than one asset cannot be stored against single-asset-types for an MCI | OLC | [5 empty] | OLC
640 | 13 | WAM UI | Assets | 2 | As a user I want to view the assets tab for an MCI | 6.7 was 6.1 |  |  |  |  | 100% | WAM
641 | 13 | WAM UI | Assets | 1 | As a user I want to store a single activity-based asset against an MCI | 6.8 was 6.1 |  |  |  |  | 100% | WAM | 2
651 |  | WAM UI | Assets | 3 | As a user I want to be able to search for assets by type | 6.12 (NEW) | [5 empty] | CCI | 2
643 | 13 | WAM UI | Assets | 1 | As a user I want to be able to replace an existing asset with different contents | 6.9 was 6.1 |  |  |  |  | 100% | WAM | 2
624.1 | 13 | WAM UI | New programme reminder | 2 | When the production details screen "Save and Close" button is pressed I want to delete the New programme reminder from FG's list, and insert the Marketing Plan reminder into KF's list. When the Marketing plan "Save" button is pressed I want to delete the New programme reminder from FG's list, and delete the Marketing Plan reminder into KF's list if it is there | 2.5 (CCI) and part of 3.1 | [5 empty] | CCI
686.2 | 13 |  | refactoring | 3 | Second part of refactor DMS sub system |  |  |  |  | 2007-05-24
642 | 13 | WAM UI | Promote / demote asset (publish) | 1 | As a user I want to make assets live, and make them unlive | 6.2 and 6.11 was 6.1 |  |  |  |  | 80% | WAM | 2
663 | 13 | WAM UI | Users | 3 | As an administrator I want to create/update users and assign them to roles | 7.4 |  |  |  |  | 100% | WAM
605 | 13 | WAM UI | Reminders | 5 | As a user, when ORAC sends a new marketable product to WAM, I want a New Programme Reminder to be created in the Owning Executive's reminder list | 8.1 (CCI) | [5 empty] | CCI
614 | 13 | WAM UI | To do list | 2 | As a user with a todo list I want to be able to see all my outstanding reminders, in prompt date order, most recent at the top | 4.3 |  |  |  | Pete 10 hours 3/5/07 | 40% | WAM
620 | 13 | WAM UI | To do list | 1 | As a user looking at my todo list I want to be able to click on a new programme reminder hyperlink and navigate to the production details tab for that MCI | 4.3 |  |  |  | Pete 6 hours 3/5/07 |  | WAM
621 | 13 | WAM UI | To do list | 3 | As a user looking at my todo list I want to be able to click the delete checkbox next to a reminder and have a confirmation screen displayed. If I confirm, then the reminder is deleted from the list. If I do not confirm the reminder stays in the list | 4.3 |  |  |  | Pete 4 hours 3/5/07 |  | WAM
30
689 | 14 | WAM UI | Assets | 2 | As a user I want to be able to create, modify, delete custom asset types so that I can add/modify assets with the required custom asset types |  |  |  |  | 2007-05-24
675 | 14 | WAM UI | Assets | 2 | As a user I want to see a single/multiple assets per asset type, to support EPK assets initially | OLC | [5 empty] | OLC
644 | 14 | WAM UI | photos | 3 | As a user I want to store one or more episode photos in WAM | 2.3 |  |  |  |  | 100% | WAM | 2
654 | 14 | WAM UI | Assets | 1 | Set up the default asset types from section 4 | section 4 | [5 empty] | WAM
646 | 14 | WAM UI | photos | 3 | As a user of WAM updating photo assets, I want all photograph assets to create, store and display a thumbnail, and publish it with the photo | (OLC) | [5 empty] | OLC | 2
686.3 | 14 |  | refactoring | 2 | Third part of refactor DMS sub system |  |  |  |  | 2007-05-24
655.1 | 14 | WAM UI | Activity templates | 2 | As an admin user viewing the admin/activities tab, I want to see a list of all Activity Templates in the system, which should include all the examples described in the use cases | 7.1
655.2 | 14 | WAM UI | Activity templates | 1 | As an admin user viewing the list of activity templates, I want to be able to view the details (read-only) of any of the templates | 7.1
634.1 | 14 | WAM UI | Activities | 2 | As a user viewing the activities tab for an MCI I want to see a list of all activities for that MCI, using dummy data for the moment. | 4.8 | [5 empty] | WAM
634.2 | 14 | WAM UI | Activities | 1 | As a user viewing the activities tab for an MCI, I want to be able to view the details of an existing activity (read only)
656 | 14 | WAM UI | Activities and assets | 1 | Set up the default activity types from section 4 | section 4 and 4.2 and 4.4 |  |  |  | Pete 0 hours 3/5/07 |  | WAM
685.1 | 14 | WAM UI | workflow | 3 | design workflow sub system part 1 |  |  |  |  | 2007-05-24
636 | 14 | WAM UI | Activities | 1 | As a user viewing an existing activity for an MCI, I want to be able to edit its details | 4.9 | [5 empty] | WAM
685.2 | 14 | WAM UI | workflow | 5 | design workflow sub system part 2 |  |  |  |  | 2007-05-24
|  |  |  | 29 | at 0.9 fp per day this would be 31 FPs
633.2 | 15 | WAM UI | Marketing plan activities | 1 | Finalise development of: As a user I want to be able to select the activities that need to be completed for the programme, from the list of default marketing activities defined in administration. (This function will only be invoked once per a programme.) | 3.4 and 4.2 and 4.4 | [5 empty] | WAM
624.2 | 15 | WAM UI | Marketing plan activities | 1 | When the save button is pressed on the create marketing plan page, the "create marketing plan reminder" is deleted.
691 | 15 | WAM UI | workflow | 1 | As a WAM user with an appropriate role (i.e. FG or KF), I want to create the marketing plan with a single create info sheet activity so that it will appear in the appropriate user's todo list
675.2 | 15 | WAM UI | Assets | 2 | As a user I want to add a name to each EPK asset and have that name displayed on OLC | OLC | [5 empty] | OLC
685.3 | 15 | WAM UI | Workflow | 2 | Write more user stories for the workflow features and document the design
613 | 15 | WAM UI | To do list | 3 | As a user with a todo list I want to be able to see all my outstanding activities, according to the prompt rules they were created with, in prompt date order, most recent at the top, colour coded correctly | 4.3 |  |  |  | Pete 13 hours 3/5/07 | 40% | WAM
623 | 15 | WAM UI | photos | 5 | As a user of WAM updating photo assets, I want to be able to upload generic photos | 2.3 | [5 empty] | CCI | 2
645 | 15 | WAM UI | photos | 5 | As a user I want to store a caption list with episode photos in WAM | 2.3 | [5 empty] | CCI | 2
616 | 15 | WAM UI | To do list | 1 | As a user looking at my todo list I want to be able to click an activity hyperlink and navigate to the MCI's Activities tab | 4.3 |  |  |  | Pete 2 hours 3/5/07 | 40% | WAM
637.1 | 15 | WAM UI | Activities | 2 | As a user I want to be able to set an activity for an MCI to complete, saving the completion date against the activity so that I can review it later. The activity should disappear from the owner's todo list. | 4.6 | [5 empty] | WAM
637.2 | 15 | WAM UI | Activities | 1 | As a user viewing a completed Non-Asset Activity, I want to be able to re-open it, so that it re-appears in the owner's todo list | 4.6
697 | 15 | WAM UI | Reminders | 3 | As a user pressing save on the marketing plan screen, I want 3 reminders to be created in the required users todo lists
649.1 | 15 | WAM UI | Activity and Task Search | 2 | As a user I want to be able to search for activities including exporting results to an Excel spreadsheet | 2.1 |  |  |  | 2007-07-17 |  | WAM
669.1 | 15 |  |  | 5 | data migration of initial assets from OLC2 to WAM | [6 empty] | WAM
604 |  | WAM UI | Withdraw programme | 2 | As a user viewing any list of Activities, if any Activity's MCI's Product's SKUs have a 'withdrawn' sales status, I want those Activities to be highlighted so that they are drawn to my attention. | 2.2 | [5 empty] | CCI
|  |  |  | 36 | initial target 37. At 0.9 fp per day this would need to be 26 FPs plus 5 for the data migration = 34 fps
669.2 | 16 |  | Data migration | 5 | report on data migration of assets form OLC2 to Wam, and ensuring additional assets come across and performance has been calculated
710 | 16 | WAM UI | Reminders | 3 | As an admin I want to be able to create and view MCI Reminder templates |  |  |  |  | 2007-08-09
712 | 16 | WAM UI | Reminders | 3 | As an administrator I expect users to see reminders associated with a reminder template with a date type of linked activity template |  |  |  |  | 2007-08-09
715 | 16 | WAM UI | Reminders | 2 | As an administrator creating a reminder template checking the "lead titles only" box I expect the system will ignore any events triggered by non-lead title MCIs |  |  |  |  | 2007-08-09
716 | 16 | WAM UI | Reminders | 1 | As an administrator I want the reminder templates specified in section 4 of the use cases (p97 of v25) to be present in the system initially |  |  |  |  | 2007-08-09
649.3 | 16 | WAM UI | Activity and Task Search | 2 | As a user I want to be able to search for activities and see results on screen (backend already built in 649.1) | 2.1
649.4 | 16 | WAM UI | Activity and Task Search | 1 | As a user I want to be able to export search results to an Excel spreadsheet | 2.1
619 |  | WAM UI | To do list | 1 | As a user looking at my todo list I want to be able to sort the columns by clicking any of the activity column headings | 4.3 |  |  |  | Pete 4 hours 3/5/07 | 40% | WAM
698 |  | WAM UI | Activities | 2 | As a user I cannot add activities unless all of the required fields have been filled out on the MCI
709.1 |  | WAM UI - Admin | Activity Templates | 3 | As an admin I expect the default activity templates to be pre-loaded in the system | 7.1
638.3 |  | WAM UI | Activities | 2 | As a admin I want to be able to cancel an activity for an MCI. | 4.6 | [5 empty] | WAM
|  |  |  | 25 | initial target 32. 40 days available (incl 5 from SK) . At 0.8 fp per day this would be 32 FPs
723 | 17 |  | servers | 5 | Set up systest /UAT servers ready for move to UAT
715 | 17 | WAM UI | Reminders | 2 | As an administrator creating a reminder template checking the "lead titles only" box I expect the system will ignore any events triggered by non-lead title MCIs |  |  |  |  | 2007-08-09
712 | 17 | WAM UI | Reminders | 3 | As an administrator I expect users to see reminders associated with a reminder template with a date type of linked activity template |  |  |  |  | 2007-08-09
700.2 | 17 | WAM UI - Activity | Activities | 2 | As a user completing an AssetType Activity I expect to be forced to save an Asset of the correct type before I can mark the Activity as completed
709.5 | 17 | WAM UI - Admin | Activity Templates | 1 | As an admin, I expect to be able specify, for an Activity Template, whether or not it should only be availlable for MCIs marked as 'lead title' | 7.1
722 | 17 | WAM UI - Admin | Activity Templates | 2 | As an admin creating a marketing plan, I expect the designer or photo executive for the Activities I create to be filled out if I've ticked the appropriate 'Assisted By' column in the template for the Activity
694 | 17 | WAM UI | Marketing Genres | 3 | As a marketing executive setting up the production details of a new MCI (or editing an existing one) in WAM, I want to be presented with the list of applicable Marketing Genres and be able to choose one as the Primary Marketing Genre, so that OLC can give this genre precedence and the OLC will look like the print catalogue
706 | 17 | WAM UI - Activities | Marketing Plan | 1 | As an admin user, I expect to see the Create Marketing Plan button until someone has created a Marketing Plan | 4.8
708 | 17 | WAMUI | Marketing plan | 1 | As a user creating a Marketing Plan, I want to be able to sort Activites by name or required so that I can find the one I'm looking for
710.1 | 17 | WAM UI - Admin | Reminder Templates | 2 | As an admin I want to be able to edit existing custom reminder templates
710.2 | 17 | WAM UI - Admin | Reminder Templates | 2 | As an admin I want to be able to create and view custom reminder templates for Activites and Tasks
714 | 17 | WAM UI | Reminders | 1 | As an administrator I expect users to see reminders associated with a reminder template with a date type of UK Tx date when the UK Tx date of an MCI is changed or the MCI is created |  |  |  |  | 2007-08-09
719 | 17 | WAM UI | Reminders | 3 | As a user I expect that reminders resulting from a custom reminder template linked to the activity template of an activity that I have completed or cancelled would be deleted by WAM |  |  |  |  | 2007-08-09
718 | 17 | WAM UI - Todo List | Reminders | 3 | As a user I expect that reminders will be generated by the system when I change the status of an activity from completed/cancelled to an open status if I have set up such reminder templates |  |  |  |  | 2007-08-09
701.2 | 17 | WAM UI - Todo List | Reminders | 1 | As a user clicking on a reminder in my todo-list, and that reminder is about an activity, I expect to be taken to the activity tab for the activity's MCI | 4.3
681 | 17 |  | refactoring | 1 | Clean up TFS |  |  |  |  | 2007-05-24
710.3 | 17 | WAM UI - Admin | Reminder Templates | 2 | As an admin I want to be able to delete existing custom reminder templates
|  |  |  | 35 | initial target 37 42 days available . At 0.8 fp per day this would be 34 FPs
707 | 18 | WAM UI | Formats | 3 | new features for formats MCIs
601 | 18 | WAM UI | Security | 5 | As the system I want to ensure that users only have access to the functions they are supposed to, ensuring that blank to-do lists are available for those users without one. | 8.3 | [5 empty] | WAM
648 | 18 | WAM UI | Programme copy | 5 | As a user I want to be able to enter weblinks into the programme copy tab so they are displayed on OLC | 2.7 |  |  |  | Pete 19 hours 3/5/07 | 100% | CCI
618 | 18 | WAM UI | Tasks | 1 | As a user looking at my todo list I want to be able to click a task and navigate to a page where I can view the task so that I can edit it | 4.3 |  |  |  | Pete 1 hours 3/5/07 | 40% | WAM
724 | 18 | WAM UI | MCI creation | 1 | As a user attempting to create an MCI, I expect the system to prevent me from creating multiple 'whole product' MCIs against the same ORAC product.
726 | 18 |  |  | 5 | Asset migration speed test and plan for executing it
727 | 18 |  |  |  | OLC feature 216 8 points - DCS work
728 | 18 |  |  | 3 | Asset search leakage
700.1 | 18 | WAM UI - Activity | Activities | 1 | As user looking at an Activity that has an Asset type, I want to see whether an Asset exists | 4.6
674 | 18 | WAM UI |  | 0 | As an Safari user I want to see the same experience as in Internet Explorer | NEW | [5 empty] | WAM
692 | 18 | WAM UI | Production details | 2 | As a marketing executive user I want to be able to specify a duration for the MCI on the production details tab so that it can be displayed on the OLC |  |  |  |  | 2007-07-17
603 | 18 | WAM UI | Programme | 3 | As a user viewing an MCI I want to see the ORAC data on the General details tab | 1.2 | [5 empty] | CCI
29
670 | 19 |  |  | 3 | send to UAT | [6 empty] | WAM
729 | 19 |  |  | 2 | migrate OLC2 assets to WAM
730 | 19 |  |  |  | As the team I want to go into UAT with no known bugs
|  |  |  | 5 | iteration 19 features. Bugs done as well
735 | 20 H |  |  | 2 | Promos and EPKs should only be allowed to be of type ".asx???" so they will play in Promo clip viewers e.g. on OLC3 |  | Bug
736 | 20 H |  |  | 1 | Episode Selection in Create MCI - episode number should be displayed |  | Additional
737 | 20 H |  |  | 2 | As a tester, I want to see at a glance which fixes are in which environment (Dev, Test, UAT, Live) |  | Bug
738 | 20 H |  |  | 3 | As a developer I want to be able to work on new features and LIVE/UAT fixes independently, so that I can release fixes confidently |  | Bug
740 | 20 H |  |  | 2 | As a creative services user opening an asset from WAM, I want to view the file if possible, rather than having it download straight to my desktop, which is annoying. If I need to set up my machine specially, WAM should give me instructions |  | Bug
741 | 20 H |  |  | 1 | I want to be able to enter Special Characters into free text fields: EPK title, MCI marketing title, Duration, all free text fields in programme copy |  | Bug
742 | 20 H |  |  | 5 | Run the asset migration into UAT and prove that everything will be migrated into Production |  | Original
731 |  |  |  |  | Fix bugs found in UAT1 (84 hours at start of iteration 20)
|  |  |  | 16 | Iteration 20 First part and majority of High priority group, together with Bugs
756 | H |  |  |  | New wam roles (general role, delete some roles, do something about developer and view only in LIVE)
743 | 21 H |  |  | 1 | As a tester I want to see a list of all existing reminders on a page in Admin |  | Additional
744 | 21 H |  |  | 3 | Calendar Control The year/month control needs to start at last year and be visible on screen |  | Bug
693 | 21 H | WAM UI | Production details | 3 | As a marketing executive user I want to be able to see in the collapsible/expandable marketing panel the name of the Indie associated with the product (data from ORAC), if there is one. If there is not I do not want to see the Indie field |  | Original
|  |  |  | 7 | iteration 21 A
671 | 21B |  |  | 5 | send to LIVE |  | Original |  |  |  |  | WAM
631 | 21B | WAM UI | Photos | 5 | As a user of WAM updating photo assets, I want to be able to upload photos in bulk | 2.3 | Original |  |  |  |  | CCI | 2
757 | 21B | WAM UI | Production details |  | As a user of the Production details page, I want to be able to enter a date into the 3 special reminder boxes and have a reminder appear for the MCI executiove named against that box.. See prototype for places.
|  |  |  | 10 | iteration 21 B
695 | M | WAM UI | Programme copy | 3 | As a user entering or amending the contents of the programme copy tab I want an email to be sent to a general "Sue Cowley" email address to show the Product title, marketing title, catalogue copy and production credits information fields. The email should say "The following product has had new/amended data in WAM which you may wish to put into ORAC." |  | Additional
699 | M | WAM UI | Contributors | 5 | As a user I want to be able to type various types of contributor names into the contributors tab for an MCI, and have the data appear on the OLC Programme Page |  | Original
659 | L | WAM UI | Festivals | 2 | As an administrator I want to be able to maintain the list of festivals | 7.7 | Original |  |  | Pete 17 hours 3/5/07 |  | CCI
704 | L | WAM UI | Festivals | 1 | As a user who can edit an Activity, I want to be able to set or change the festival, including via the Marketing Plan | 4.9 | Original
758 |  | WAM UI | Photos | 5 | Change the way photos are linked to the MCI data so that, if the database IDs are lost, we can recover the assets.
|  |  |  | 16 | By the end of OLC3 go live
Backlog: | [10 empty] | v1 % done
ID | Iteration | Surface Point | Theme | Pts | Feature | Satisfaction Criteria | Work Type | Business Risk | Tech Risk | Reviewed | % built in V1.0 |  | Phase
635 | M | WAM UI - Activity | Activities | 1 | As a user viewing the activities tab for an MCI, I want to be able to create new activities from the existing templates in the system, adding back all of the "leakage" from the earlier simple views of activities | 4.1 | Original |  |  |  |  | WAM
734 | M |  |  | 5 | Data cleansing tool for Creative Services to do contributor data etc. |  | Additional
735 | M |  |  | 3 | As a view only user on the Show Photo page I should only be given a thumbnail so that I cannot distribute files I don't have rights to. |  | Additional
736 | M |  |  | 2 | As a WAM users, when I click on save on Programme copy and Production details tabs I want to be able to see an error message when there are some errors. I do not want to have the error messages on a part of the page I cannot see in front of me |  | Additional
737 | M |  |  | 0 | Bug 2064. As a user searching for activities and tasks I should have to complete at least one search parameter |  | Additional
738 | M |  |  | 1 | As a developer I want to see a diagnostics page to show the health of the ORAC to WAM messaging link. |  | Additional
664.2.1 | M | WAM UI - Admin | Re-allocate | 2 | As an admin, I want to be able to be able to replace the person in a single-member role so that the reminders associated with that role are re-allocated to the new person | 7.3 | Original
664.2.2 | M | WAM UI - Admin | Re-allocate | 5 | As an admin, I want to be able to view a particular user's current responsibilities to MCIs, Activities or Tasks, and re-allocate then (and thus any associated reminders) to another user | 7.3 | Original
690 | M | WAM UI - Admin | Re-allocate | 1 | As an admin, I cannot deactivate a user unless their responsibilities have all been re-allocated |  | Original
|  |  |  | 20 | in Medium priority group
739.2 | L |  |  |  | As a user viewing an MCI photos tab I want the sort order to be by Version, then within eacvh veraion, Generic first then Episodes in order, and within generic and episode, by photo name.
739.3 | L |  |  |  | As a user viewing Programme search results, I want the MCI titles to be in ascending alphabetical order within their product
739.4 | L |  |  |  | As a user viewing the Asset search tab and the MCI Activity tab I want all columns to be sortable
739.1 | 21 H |  |  | 5 | As a user viewing tabulated data, I want it to be sorted, by default, in a logical way. (see high priority card for more details) |  | Additional
618 | L | WAM UI | Tasks | 1 | As a user looking at my todo list I want to be able to click a task and navigate to a page where I can view the task so that I can edit it | 4.3 | Original |  |  | Pete 1 hours 3/5/07 | 40% | WAM
649.2 | L | WAM UI | Tasks | 1 | As a user I want to be able to search for tasks including exporting results to an Excel spreadsheet | 2.1 | Original |  |  | 2007-07-17 |  | WAM
650 | L | WAM UI | Tasks | 5 | As a user I want to be able to create, amend and complete a task, uploading the asset if there is one associated with the task | 5.1, 5.3 and 5.5 | Original |  |  |  |  | WAM | part in 2
658 | L | WAM UI | Tasks | 1 | Set up the default task types from section 4 | section 4 and 4.2 and 4.4 | Original |  |  |  |  | CCI
720 | L | WAM UI | Tasks | 2 | As an admin, I want to be able to specify whether a custom asset type is an "Activity" or "Task" asset so that the appropriate list of asset types is offered when creating a new task or activity template |  | Original
701.3 | L | WAM UI - Todo List | Tasks | 1 | As a user clicking on a reminder, I expect to be taken to the 'view task' page if it's about a task. | 4.3 | Original
615 | L | WAM UI | Tasks | 2 | As a user with a todo list I want to be able to see all my outstanding tasks, colour coded correctly | 4.3 | Original |  |  | Pete 13 hours 3/5/07 | 40% | WAM
711 | L | WAM UI | Tasks | 3 | As an administrator I expect users to see reminders associated with a reminder template with a date type of 'linked task template due date rule' |  | Original |  |  | 2007-08-09
721 | L | WAM UI | Tasks | 3 | As a user I want to be able to store and retreive non-MCI-related assets, i.e. any AssetType marked 'Task' (see #720) |  | Original
717 | L | WAM UI - Admin | Activity Templates | 5 | As a user I would like to be able to create and edit activity templates | 7.1 | Original |  |  | 2007-08-09
732 |  |  |  |  | Fix bugs found in UAT 2
709.3 | L | WAM UI - Admin | Activity Templates | 1 | As an admin, I expect the system to stop me from changing the Asset Type for locked down templates | 7.1 | Original
745 | L |  |  | 2 | As a user if I check all episodes of a single-SKU MCI and press save, then it should become and be validated as a whole product MCI. |  | Additional
746 |  |  |  | 3 | As a photo user I want the photo notes field on the production details to allow me to insert limitless text with each entry to have user name and date. |  | Additional
747 |  |  |  | 1 | Show TX Season and Tx Year and Tx channel as new columns in the existing SKU table (see bug 2046) |  | Bug
748 |  |  |  | 3 | As an admin, when I change a reminder template prompt rule, I want the right effect on existing reminders - discuss with Kerry first the approach to recalculation and the effect on todo lists. |  | Additional
749 |  |  |  | 2 | As a users I want to be able to search for assets by festival |  | Additional
750 |  |  |  | 3 | As a user I would like the effect of pressing the cancel button to be as if I had pressed the Back button so that the previous page does not have to reload and slow me down |  | Additional
751 |  |  |  | 2 | As a user I would like to see the Programme Image, if there is one, on the various MCI tabs, as shown in the MCI prototype |  | Additional
752 |  |  |  | 3 | As an admin, when I change an activity template prompt rule, I want the right effect on existing activities - discuss with Kerry first the approach to recalculation and the effect on todo lists. |  | Additional
753 |  |  |  | 1 | As a user I want the system to ensure that each Asset type can only be related to one activity template (needs an appropriate error message in the activity template edit screen) |  | Bug
754 |  |  |  | 2 | As a user attempting to add an asset of a particular type when one already exists on that MCI I want instant feedback and the option to edit/replace the existing asset |  | Additional
755 |  |  |  | 1 | Update reminder templates so a user can choose which task I want my reminder template to be linked to. |  | Original
|  |  |  | 53 | in low priority group
On Hold
665 | ON HOLD | WAM UI | Generate report | ON HOLD | As an authorised user, I want to be able to run the predefined Print Schedule report which will report on programmes and associated activities. | 8.5 | [5 empty] | WAM
672 | NICE TO HAVE | WAM UI | Users | NICE TO HAVE | As an authorised user searching for users, I would like to be able to search by name, rather than have to page through the list of users.
708.2 | ON HOLD | WAM UI | Marketing Plan | ON HOLD | As an admin maintaining activity templates, I want to be able to set the order that activities will be displayed to a user when the create a marketing plan so that the user can find them as quickly as possible on the marketing plan.
Next Feature:759
[5 empty] | Summary of Original/Additional/Bug features after UAT |  |  | High | Medium | Low | check = 0
| proposing to defer 43 of 56 points of original features |  |  |  | Points of original features |  | 61 | 26 | 9 | 26 | 0
| proposing to defer 31 of 41 points of additional features |  |  |  | Additional features as a result of UAT and System testing |  | 41 | 5 | 11 | 25 | 0
| proposing to defer 2 of 15 points of bugs |  |  |  | Features created to address bugs (84 hours of bugs as well) |  | 15 | 13 | 0 | 2 | 0
[5 empty] | Check total should be zero |  | #REF!
Notes
copy of OLC 311 |  |  |  |  | If a new Asset is added via WAM to the DMS that relates to a MarketingCatalogueItem that is not active to the OLC, nothing needs to happen
copy of OLC 313 |  |  |  |  | If a MarketingCatalogueItem is moved from 'unpublished' to 'published' state in WAM, all related assets in the WAM DMS should be uploaded (or have already been uploaded) to the CDN so that clients can see them via the OLC
[5 empty] | Summary | days |  | %
[5 empty] | Total above (this estimate excludes iteration 7 as it was done after iteration 7 had been completed) | 34 |  | 21.12%
[5 empty] | Points above to be used in "porting" functionality from CCI or as a result of changes needed to make WAM/CCI work together | 72 |  | 44.72%
[5 empty] | Points above incurred because of OLC requirements and WAM/OLC testing requirements | 10 |  | 6.211%
[5 empty] | Other WAM work still to be completed (including code to be refactored out of UI into new system structure | 79 |  | 49.07%
[5 empty] | Check Total | 161 |  | 100%
error of -127
[5 empty] | WAM estimate based on 259 feature points as at start of iteration 8 | days |  | £ @350
[5 empty] | 259 points = 259 developer days. = 5 iterations of 5 people | 259 |  | 90650
designer screen revisions (all related to CCI or knock on effect of WAM/CCI review by Kate/Kerry
[5 empty] | tester at 2 days per week. Each week of 25 points, therefore 20 days | 20 |  | 7000
[5 empty] | Kerry 15 days for test scripts, 8 for UAT, 5 for UAT WAM/OLC, 20 for business ready tasks, plus 1 day per 25 pts | 43 |  | 15050
[5 empty] | project manager nil as already in OLC case | 0 |  | 0
112700
[5 empty] | spent so far 85k????? Should this include what we have actually spent or just what we have reported |  |  | 85000
[5 empty] | therefore Total |  |  | 197700

## Iteration Summary (OLC)
Iteration # | Iteration end date | Feature Points Attempted | Feauture Pts Completed | Feature Points Carried Forward | New Features Discovered | Feature Points in Backlog (at Start) | Target Feature Points at end (0.9) | Feature Points in Backlog (at end) | Hours of bug fixes outstanding | Team's Estimated Manhours | Actual Man-hours Used | Actual Man-days Used | Pts Delivered / Actual Man Day | Estimated : Actual Man Hours | Calendar man days used | Pts Delivered / Calendar Man Day | FPS at 0.7
0 | [7 empty] | 638
1 |  |  | 94 |  |  |  |  | 544 | ? | 298 | 317.5 | 45.3571 | 2.0724 | 1 : 1.1
2 |  |  | 81 |  |  |  |  | 463 | 28.5 | 187 | 274 | 39.1429 | 2.0693 | 1 : 1.5
3 |  |  | 47 |  |  |  |  | 416 | 23 | 210 | 326 | 46.5714 | 1.0092 | 1 : 1.6
4 |  |  | 68 |  |  |  |  | 348 | 22 | 185 | 503 | 71.8571 | 0.94632 | 1 : 2.7
5 |  |  | 62 |  |  |  |  | 269 | 22 | 267 | 390 | 55.7143 | 1.1128 | 1 : 1.5
6 |  |  | 50 |  |  |  |  | 457 |  |  | 301.75 | 43.1071 | 1.1599 |  | 40.5 | 1.2346
a
7 | 2007-04-20 | 47 | 45 | 6 | 6 | 740 |  | 522 |  | 325 | 351 | 50.1429 | 0.89744 | 1 : 1.1 | 46 | 0.97826
8 | 2007-05-04 | 53 | 53 | 0 | 0 | 868 |  | 466 |  | 320 | 293 | 41.8571 | 1.2662 | 1 : 0.9
9 | 2007-05-18 | 38 | 37 |  |  | 803 |  | 434 |  | 168 | 228.5 | 32.6429 | 1.1335 | 1 : 1.4
10 | 2007-06-01 |  | 39 | 0 | 0 | 780 |  | 395 |  |  | 191.5 | 27.3571 | 1.4256
11 | 2007-06-15 | 48 | 48 | 0 | 0 |  |  | 349 |  |  | 316 | 45.1429 | 1.0633
12 | 2007-06-29 | 28 | 34 | 0 | 0 |  |  | 315 |  |  | 324.5 | 46.3571 | 0.73344
13 | 2007-07-13 | 15 | 15 | 0 | 0 |  |  | 300 |  |  | 146 | 20.8571 | 0.71918
14 | 2007-07-27 | 26 | 25 |  |  |  |  | 275 |  |  | 179 | 25.5714 | 0.97765
15 | 2007-08-10 | 27 | 25 | 2 |  |  |  | 252 |  |  | 159.5 | 22.7857 | 1.0972
16 | 2007-08-24 | 23 | 21 |  |  |  |  | 231 |  |  | 96 | 13.7143 | 1.5312
17 | 2007-09-07 | 17 | 21 |  |  |  |  | 210 |  |  | 163 | 23.2857 | 0.90184
18 | 2007-09-21 | 8 | 5 |  |  |  |  | 205 |  |  | 21 | 3 | 1.6667
19 | 2007-10-05 | 0 | 0 |  |  |  |  | 205
20 | 2007-10-19 | 0 | 0 |  |  |  |  | 205
21 | 2007-11-02 | 9 | 9 |  |  |  |  | 209
22 | 2007-11-16 | 45 | 42 | 3 | 11 |  |  | 178 |  |  | 451.1 | 64.4429 | 0.65174
23 | 2007-11-30 | 49 | 27 |  |  |  |  | 175 |  |  | 405 | 57.8571 | 0.46667
24 | 2007-12-14 | 45 | 38 |  |  |  |  | 137 |  |  | 316.5 | 45.2143 | 0.84044
25 | 2007-12-28 | [5 empty] | 127 | [9 empty] | 127
26 | 2008-01-11 | 40 | 24 |  |  |  | 97 |  |  |  | 329.75 | 47.1071 | 0.50948 |  |  |  | 101
27 | 2008-01-25 | [5 empty] | 45 | [9 empty] | 56
28 | 2008-02-08 | [5 empty] | 0 | [9 empty] | 0
29 | 2008-02-22 | [5 empty] | 0 | [9 empty] | 0
|  |  | 484 | [8 empty] | 520.2286 | 0.93036
Formulas:
Iteration end date = [Iteration end date, row below]-14
Iteration end date = [Iteration end date, row above]+14

## Iteration Summary (WAM)
Iteration # | Iteration end date | Feature Points Attempted | Feauture Pts Completed | Feature Points Carried Forward | New Features Discovered | Feature Points in Backlog (at Start) | Target Feature Points at end | Feature Points in Backlog (at end) | Hours of bug fixes outstanding | Team's Estimated Manhours | Actual Man-hours Used | Actual Man-days Used | Pts Delivered / Actual Man Day | Estimated : Actual Man Hours | Calendar man days used | Pts Delivered / Calendar Man Day
0
1
2
3
4
5
6
7 | 2007-04-20 |  | 15 |  |  |  |  | 304 |  |  |  | 0 | 1.66 | #DIV/0!
8 | 2007-05-04 |  | 9 |  |  |  |  | 295 |  |  |  | 0 | 1.28 | #DIV/0!
9 | 2007-05-18 |  | 9 |  |  |  |  | 286 |  |  |  | 0 | 0.6 | #DIV/0!
10 | 2007-06-01 |  | 17 |  |  |  |  | 269 |  |  |  | 0 | 0.92
11 | 2007-06-15 | 14 | 14 | 0 | 3 |  |  | 258 |  |  | 120 | 17.1429 | 0.81667
12 | 2007-06-29 | 37 | 21 |  | 9 |  |  | 246 |  |  | 168.5 | 24.0714 | 0.8724
13 | 2007-07-13 | 40 | 30 |  |  |  |  | 216 |  |  | 262 | 37.4286 | 0.80153
14 | 2007-07-27 | 41 | 29 |  |  |  |  | 187 |  |  | 248.5 | 35.5 | 0.8169
15 | 2007-08-10 | 40 | 34 |  |  |  |  | 153 |  |  | 261 | 37.2857 | 0.91188
16 | 2007-08-24 | 37 | 25 |  |  |  |  | 128 |  |  | 293.5 | 41.9286 | 0.59625
17 | 2007-09-07 | 37 | 35 |  |  |  |  | 93 |  |  | 270 | 38.5714 | 0.90741
18 | 2007-09-21 | 35 | 29 |  |  |  |  | 64 |  |  | 430.5 | 61.5 | 0.47154
19 | 2007-10-05 | 21 |  |  |  |  | 47
20 | 2007-10-19 | 38 |  |  |  |  | 0
21 | 2007-11-02 | 5 |  |  |  |  | 5
Formulas:
Iteration end date = [Iteration end date, row below]-14
Iteration end date = [Iteration end date, row above]+14

## Summary (Both)
|  | Latest completed sprint: | 17
|  | WAM Target Release Sprint: | 19
|  | Velocity Required: | 36 | (update this value manually)
# | WAM Points | WAM Backlog | Sprints Remaining | Points / Sprint Required | WAM Target Backlog | OLC Points | OLC Backlog | Total Backlog | Days Worked | Velocity | NormalisedVelocity
1 | 0 | 0 | 18 |  | 648 | 94 | 544 | 1192 | 45.3571 | 94 | 2.0724
2 | 0 | 0 | 17 |  | 612 | 81 | 463 | 1075 | 39.1429 | 81 | 2.0693
3 | 0 | 0 | 16 |  | 576 | 47 | 416 | 992 | 46.5714 | 47 | 1.0092
4 | 0 | 0 | 15 |  | 540 | 68 | 348 | 888 | 71.8571 | 68 | 0.94632
5 | 0 | 0 | 14 |  | 504 | 62 | 269 | 773 | 55.7143 | 62 | 1.1128
6 | 0 | 0 | 13 |  | 468 | 50 | 457 | 925 | 43.1071 | 50 | 1.1599
7 | 15 | 304 | 12 | 25.3333 | 432 | 45 | 522 | 954 | 50.1429 | 60 | 1.1966
8 | 9 | 295 | 11 | 26.8182 | 396 | 53 | 466 | 862 | 41.8571 | 62 | 1.4812
9 | 9 | 286 | 10 | 28.6 | 360 | 37 | 434 | 794 | 32.6429 | 46 | 1.4092
10 | 17 | 269 | 9 | 29.8889 | 324 | 39 | 395 | 719 | 27.3571 | 56 | 2.047
11 | 14 | 258 | 8 | 32.25 | 288 | 48 | 349 | 637 | 62.2857 | 62 | 0.99541
12 | 21 | 246 | 7 | 35.1429 | 252 | 34 | 315 | 567 | 70.4286 | 55 | 0.78093
13 | 30 | 216 | 6 | 36 | 216 | 15 | 300 | 516 | 58.2857 | 45 | 0.77206
14 | 29 | 187 | 5 | 37.4 | 180 | 25 | 275 | 455 | 61.0714 | 54 | 0.88421
15 | 34 | 150 | 4 | 37.5 | 144 | 25 | 252 | 396 | 60.0714 | 59 | 0.98216
16 | 25 | 128 | 3 | 42.6667 | 108 | 21 | 231 | 339 | 55.6429 | 46 | 0.8267
17 | 35 | 93 | 2 | 46.5 | 72 | 21 | 210 | 282 | 61.8571 | 56 | 0.90531
18 |  |  | 1 |  | 36 |  |  | 36
19 |  |  | 0 |  | 0 |  |  | 0
20 | [7 empty] | 0
21 | [7 empty] | 0
22 | [7 empty] | 0
23 | [7 empty] | 0
24 | [7 empty] | 0
25 | [7 empty] | 0

## OLC migration
OLC3 migration tasks
| From | To | What | Feature # | FPs
1 | ORAC | OLC Admin | Product catalogue metadata including genres | ? | ?
2 | ORAC | OLC | Product catalogue metadata including genres | ? | ?
3 | ORAC | Discus Service | Product catalogue metadata including genres | 239 | 2
4 | ORAC | Preview Service | Product catalogue metadata including genres | 240 | 2
5 | WAM | OLC Admin | MCI metadata
6 | WAM | OLC | MCI metadata
7 | Discus | AAS | Discus assets and metadata | 415 | 13
8 | Discus | Akamai | Discus assets and metadata | " " | " "
9 | Preview | AAS | Preview assets and metadata | 19 | done in iteration 10
10 | Preview | Akamai | Preview assets and metadata
11 | OLC2 | OLC | After sales tokens | 433 | done in iteration 16
12 | OLC2 | OLC | Preview tokens | 430 | done in iteration 12
13 | OLC2 | OLC | Users | 113 | done in iteration 11
14 | OLC2 | SSO | Users | ? | " " ?
15 | OLC2 | SSO | Users | ? | " " ?
16 | WAM | AAS | WAM assets and metadata | 416 data | 20
17 | WAM | Akamai | WAM assets and metadata | 432 assets | 5
|  |  | User favourites | 139, 431 | zeroed from 7 points | Don’t do it.

## Printing
ID | Iteration | Surface Point | Theme | Pts | Feature | Satisfaction Criteria
OLC |  | 3 | 4 | 5 | 7 | 6
208.5 |  | OLC UI | Search results | 5 | As a user of the OLC, I want to be able to search the catalogue quickly and easily so that I can find programmes that I am interested in. | Conditions of Satisfaction Doc
208.5 |  | OLC UI | Search results | 5 | As a user of the OLC, I want to be able to search the catalogue quickly and easily so that I can find programmes that I am interested in. | Conditions of Satisfaction Doc
WAM |  | 3 | 4 | 5 | 6 | 7
699 |  | WAM UI | Contributors | 5 | As a user I want to be able to type various types of contributor names into the contributors tab for an MCI, and have the data appear on the OLC Programme Page | 0
699 |  | WAM UI | Contributors | 5 | As a user I want to be able to type various types of contributor names into the contributors tab for an MCI, and have the data appear on the OLC Programme Page | 0

## LookUps
Risk | Feature Point Scale: | Milestone Release | Status
Low | 0 | OLC 3.0.0 (beta) "Search" | To do
Medium | 1 | OLC 3.0.1 (beta) "Previews" | Development
High | 2 | OLC 3.0.2 (beta) "Showcase" | Systest
| 3 | OLC 3.0.3 (beta) "Pre-Sales in After-Sales" | UAT
| 5 | WAM 1.3 (live) "Photos" | Waiting for Live
| 8 | OLC 3.0.4 (beta) "Photos in After-Sales" | Live
| 13 | OLC 3.0.5 (beta) "Discus in After-Sales" | Deleted
| 20 | OLC 3.0.6 (live) "Fine tuning" | Hold
OLC 3.0.7 (live) "Go-Live"
| 40 | OLC 3.0.8 (live) "Service Pack"
| 100 | OLC 3.0.2.1 (Users and Admin)